## Summary
KANDO - Stage 1 (foundation): Test Report
Full suite on branch stage-1 after the final fix wave (final whole-branch review findings and parked items fixed), run 27 October 2026: web integration tests on the local Docker database, app and package unit tests. No phone or browser check was done; features that only a phone can confirm are marked Not yet done (phone) in Other Checks.
Measure | Value
Automated tests
Passed
Failed
Skipped
Web test files | 32
App test suites | 12
Package tests (contract 7, i18n 9) | 16
Parity rows: Passed / Not yet done (phone) / Open | 18 / 4 / 0

## Test Results
Area | Test file | Test (what it checks) | Part | Outcome
Admin back office API | admin-api.int.spec.ts | lists documents with the pending ones first, with owner email | Web | Passed
Admin back office API | admin-api.int.spec.ts | approving a document makes the service offerable and records the reviewer | Web | Passed
Admin back office API | admin-api.int.spec.ts | rejecting stores the note, and needs one | Web | Passed
Admin back office API | admin-api.int.spec.ts | suspending a user hides the provider from search and the public page; lifting shows it again | Web | Passed
Admin back office API | admin-api.int.spec.ts | a user suspended before having a profile cannot create one and publish it (409) | Web | Passed
Admin back office API | admin-api.int.spec.ts | lists users with pagination and a text filter on email or name | Web | Passed
Admin back office API | admin-api.int.spec.ts | creates and updates a category per language | Web | Passed
Admin back office API | admin-api.int.spec.ts | creates a page and publishes it | Web | Passed
Admin back office API | admin-api.int.spec.ts | sets a staff role by email; an unknown email is 404 | Web | Passed
Admin back office API | admin-api.int.spec.ts | providers are readable; a Reviewer deletes a photo (object removed, published profile photo unpublishes) | Web | Passed
Admin back office API | admin-api.int.spec.ts | GET /me returns the staff user; unknown resources are 404 | Web | Passed
Admin back office API | admin-api.int.spec.ts | a Reviewer cannot decide their own document | Web | Passed
Admin back office API | admin-api.int.spec.ts | an expired suspension is not counted by the suspended filter | Web | Passed
Staff roles | admin-roles.int.spec.ts | a Reviewer cannot do Administrator actions, and nothing changes | Web | Passed
Staff roles | admin-roles.int.spec.ts | a Reviewer cannot change or delete an existing category or page | Web | Passed
Staff roles | admin-roles.int.spec.ts | a Reviewer can read users and documents | Web | Passed
Staff roles | admin-roles.int.spec.ts | a customer with no staff role gets 403 on every admin route; no session gets 401 | Web | Passed
Staff roles | admin-roles.int.spec.ts | the last Administrator cannot be demoted | Web | Passed
Staff roles | admin-roles.int.spec.ts | every route file under app/api/admin exports handlers built with adminRequest | Web | Passed
Security rule check | app-endpoints-wrapped.int.spec.ts | the owner-connection check catches a bypass (negative fixture) | Web | Passed
Security rule check | app-endpoints-wrapped.int.spec.ts | every route file under app/app-api exports handlers built with appRequest | Web | Passed
App request wrapper | app-request.int.spec.ts | first contact creates the users row | Web | Passed
App request wrapper | app-request.int.spec.ts | a forged cookie is 401 and touches nothing | Web | Passed
App request wrapper | app-request.int.spec.ts | required auth without a cookie is 401 | Web | Passed
App request wrapper | app-request.int.spec.ts | optional auth without a cookie runs with no user | Web | Passed
App request wrapper | app-request.int.spec.ts | an unconfirmed email: 403 where auth is required, signed out where optional; never a users row | Web | Passed
App request wrapper | app-request.int.spec.ts | a handler error rolls back and returns 500 | Web | Passed
App request wrapper | app-request.int.spec.ts | a body over maxBodyBytes is 413 before the handler runs | Web | Passed
App request wrapper | app-request.int.spec.ts | user A cannot read user B through the wrapper | Web | Passed
App request wrapper | app-request.int.spec.ts | app_user cannot write staff columns of its own row | Web | Passed
App request wrapper | app-request.int.spec.ts | first contact with a changed email updates the row | Web | Passed
App request wrapper | app-request.int.spec.ts | a second id with the same email gets 409 and no row is written | Web | Passed
App request wrapper | app-request.int.spec.ts | a thrown 400 Response is returned unchanged | Web | Passed
Sign-up and session | auth-cookie-flow.int.spec.ts | signs up by REST, captures the cookie; /app-api/v1/me knows the session but refuses it until the email is confirmed | Web | Passed
Categories | categories.int.spec.ts | ordered by sort, "other services" always last, names in the requested language, anonymous allowed | Web | Passed
Categories | categories.int.spec.ts | an unknown language is 400 | Web | Passed
Concurrency | concurrency.int.spec.ts | 12 concurrent searches and 12 concurrent public pages all complete | Web | Passed
Database migrations | db-migrations.int.spec.ts | migrates an empty database and classifies every table | Web | Passed
Emails | email.int.spec.ts | approval: one email in the user language with the document name and the deep link | Web | Passed
Emails | email.int.spec.ts | rejection in German includes the note verbatim, escaped in the HTML | Web | Passed
Emails | email.int.spec.ts | without a key it only logs and records, and never throws | Web | Passed
Emails | email.int.spec.ts | outside tests without a key: one log line without recipient or body, and nothing kept in memory | Web | Passed
Emails | email.int.spec.ts | with a key it calls Resend with the full message; an { error } and a throw are logged, not thrown | Web | Passed
Emails | email.int.spec.ts | an unexpected stored language falls back to German | Web | Passed
Uploads and document review | files-review.int.spec.ts | afterCommit: a handler that deletes a photo and then throws rolls back, the object stays | Web | Passed
Uploads and document review | files-review.int.spec.ts | afterCommit: the object is deleted only after the commit | Web | Passed
Uploads and document review | files-review.int.spec.ts | private_files and documents are isolated (RLS) | Web | Passed
Uploads and document review | files-review.int.spec.ts | at most 10 unsubmitted uploads per user (409) | Web | Passed
Uploads and document review | files-review.int.spec.ts | a decompression bomb and a header followed by garbage are 400; a later upload is accepted | Web | Passed
Uploads and document review | files-review.int.spec.ts | EXIF is stripped from the stored JPEG | Web | Passed
Uploads and document review | files-review.int.spec.ts | alt over 200 characters is 400 | Web | Passed
Uploads and document review | files-review.int.spec.ts | an unauthenticated upload is refused before the body is read | Web | Passed
Uploads and document review | files-review.int.spec.ts | the body is read before the first-contact user row and the transaction exist | Web | Passed
Uploads and document review | files-review.int.spec.ts | photos of a published provider are public, and unreadable once suspended | Web | Passed
Uploads and document review | files-review.int.spec.ts | replacing the profile photo of a published profile works | Web | Passed
Uploads and document review | files-review.int.spec.ts | deleting the profile photo while publishing never leaves a published profile without a photo | Web | Passed
Uploads and document review | files-review.int.spec.ts | two simultaneous submits for one requirement give one 201 and one 409 | Web | Passed
Uploads and document review | files-review.int.spec.ts | the database refuses a second pending check for a requirement | Web | Passed
Uploads and document review | files-review.int.spec.ts | approval (staff SQL) makes a service with required documents offerable | Web | Passed
Uploads and document review | files-review.int.spec.ts | the signed link carries X-Amz-Expires=300 and the public URL needs AWS_ENDPOINT | Web | Passed
Uploads | files.int.spec.ts | a profile photo is re-encoded to JPEG at most 1600 px and returned in contract shape | Web | Passed
Uploads | files.int.spec.ts | a new profile photo replaces the old one and deletes its object | Web | Passed
Uploads | files.int.spec.ts | portfolio is limited to 12 (409), a non-image is 400, a missing kind is 400 | Web | Passed
Uploads | files.int.spec.ts | a photo needs a profile first (409); anonymous is 401; an oversize body is 413 | Web | Passed
Uploads | files.int.spec.ts | deleting a photo: another user gets 404, the owner 204 and the object is gone; the profile photo is cleared | Web | Passed
Uploads | files.int.spec.ts | the profile photo of a published profile cannot be deleted (409) | Web | Passed
Uploads | files.int.spec.ts | photo_id is domain-only and photos are isolated | Web | Passed
Uploads | files.int.spec.ts | files: a PDF goes to the private bucket, a non-PDF is 400, another user gets 404, the owner a signed link | Web | Passed
Uploads | files.int.spec.ts | documents also take JPEG, PNG and WEBP photos: re-encoded without metadata, at most 2400 px, stored with their type | Web | Passed
Uploads | files.int.spec.ts | a GIF and a text file renamed to .pdf are refused as documents | Web | Passed
Uploads | files.int.spec.ts | staff open an image document through the same signed link; it is served as an image | Web | Passed
Uploads | files.int.spec.ts | a failed file insert removes the uploaded object | Web | Passed
Uploads | files.int.spec.ts | verifications: one pending check per requirement (409 removes the second file), bad input is 400 | Web | Passed
Website home page | home-page.int.spec.ts | is German by default: headline, categories, store badges without links, no forbidden words | Web | Passed
Website home page | home-page.int.spec.ts | switches to English with ?lang=en and falls back to German for unknown values | Web | Passed
Website home page | home-page.int.spec.ts | has per-language metadata with canonical and hreflang for every language | Web | Passed
Website home page | home-page.int.spec.ts | metadataBase makes canonical and hreflang absolute on the site url | Web | Passed
Website home page | home-page.int.spec.ts | html lang follows the request language; unknown falls back to de | Web | Passed
Website home page | home-page.int.spec.ts | footer links the four legal pages with catalogue labels in both languages | Web | Passed
Database connection | owner-connection.int.spec.ts | inside a request transaction the owner connection `db` is a different connection (not app_user) | Web | Passed
Database connection | owner-connection.int.spec.ts | two interleaved requests keep their own user id and role | Web | Passed
Legal and info pages | pages.int.spec.ts | every table is classified (pages and page_texts are public reference tables) | Web | Passed
Legal and info pages | pages.int.spec.ts | anonymous app requests read pages but cannot write them | Web | Passed
Legal and info pages | pages.int.spec.ts | returns the text in the language, falls back to de, hides drafts and unknown slugs | Web | Passed
Legal and info pages | pages.int.spec.ts | publishedPages lists published pages only | Web | Passed
Legal and info pages | pages.int.spec.ts | renders the Markdown body in both languages with the de fallback | Web | Passed
Legal and info pages | pages.int.spec.ts | 404 for unknown and unpublished slugs | Web | Passed
Legal and info pages | pages.int.spec.ts | metadata: title, canonical and hreflang for every language | Web | Passed
Legal and info pages | pages.int.spec.ts | escapes HTML in a body and drops unsafe links | Web | Passed
Legal and info pages | pages.int.spec.ts | escapes raw html and keeps Markdown | Web | Passed
Legal and info pages | pages.int.spec.ts | external links get rel="nofollow ugc"; protocol-relative and backslash paths are dropped | Web | Passed
Postcodes | postcodes.int.spec.ts | imports the German file and looks up 01053 Dresden | Web | Passed
Postcodes | postcodes.int.spec.ts | rejects a four-digit German code and an unknown one | Web | Passed
Postcodes | postcodes.int.spec.ts | Berlin to Munich is about 504 km | Web | Passed
Website provider page | provider-page.int.spec.ts | German default: headline, public name, category, price "ab 80,00 €", on request, place | Web | Passed
Website provider page | provider-page.int.spec.ts | English with ?lang=en: "from €80.00" | Web | Passed
Website provider page | provider-page.int.spec.ts | escapes user content | Web | Passed
Website provider page | provider-page.int.spec.ts | 404 for a hidden provider (draft) and an unknown slug | Web | Passed
Website provider page | provider-page.int.spec.ts | metadata: title, description, canonical and hreflang for every language | Web | Passed
Website provider page | provider-page.int.spec.ts | is shown only when the texts are not in the page language | Web | Passed
Website provider page | provider-page.int.spec.ts | ?translate=1 shows the translation with the AI label, noindex, canonical unchanged | Web | Passed
Website provider page | provider-page.int.spec.ts | ?translate=1 without a key shows the original texts and the unavailable copy | Web | Passed
Website provider page | provider-page.int.spec.ts | translate=1 on texts already in the viewer language: original, no label, no model call | Web | Passed
Provider profile | provider-profile.int.spec.ts | GET is null when there is no profile | Web | Passed
Provider profile | provider-profile.int.spec.ts | PUT creates (201) and a later PUT edits (200); responses fit the contract | Web | Passed
Provider profile | provider-profile.int.spec.ts | an unknown postcode is 400 and changes nothing | Web | Passed
Provider profile | provider-profile.int.spec.ts | first save needs displayName and providerType; a business needs a business name | Web | Passed
Provider profile | provider-profile.int.spec.ts | status, slug and suspended in the body are ignored | Web | Passed
Provider profile | provider-profile.int.spec.ts | one user's profile is not visible to another | Web | Passed
Provider profile | provider-profile.int.spec.ts | an invalid body is 400 with the contract error | Web | Passed
Provider profile | provider-profile.int.spec.ts | an unconfirmed email gets 403 EMAIL_NOT_VERIFIED from PUT provider-profile and GET /me, and no users row | Web | Passed
Provider profile | provider-profile.int.spec.ts | PATCH /me checks its body with the contract: 400 Invalid input names the field; a valid patch saves | Web | Passed
Public provider data | provider-public.int.spec.ts | a published provider page: contract shape, place, photo urls, only offerable services | Web | Passed
Public provider data | provider-public.int.spec.ts | 404 when not visible: unknown, draft, or no offerable service | Web | Passed
Public provider data | provider-public.int.spec.ts | a draft page is a 404 for its own owner too | Web | Passed
Public provider data | provider-public.int.spec.ts | unknown language is 400 | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | returns translated texts in the page shape | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | a draft or suspended provider -> 404, no call | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | unknown lang -> 400 | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | service failure -> 503 and nothing stored | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | a logged-in caller is counted under the user id | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | the provider endpoint reports translatable per viewer language | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | accepts no text from the client | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | fails closed without a usable secret: 503, no counter row, no model call | Web | Passed
Site and admin routing | proxy.int.spec.ts | /admin and below go through the auth middleware | Web | Passed
Site and admin routing | proxy.int.spec.ts | /administrator or a page slug starting with admin is a site path with x-lang | Web | Passed
Public name | public-name.int.spec.ts | publicNameFor: business name, else first name and surname initial | Web | Passed
Public name | public-name.int.spec.ts | slugify transliterates umlauts and strips the rest | Web | Passed
Public name | public-name.int.spec.ts | public name and slug are unique and stable | Web | Passed
Public name | public-name.int.spec.ts | an individual without an account name gets a slug from the display name, never "profile" | Web | Passed
Public name | public-name.int.spec.ts | first contact copies the account name from the session; a later contact does not overwrite it | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | the first-time flow: refused until photo and service exist, then published, then unpublished | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | a postcode-less profile is refused unless it works remotely | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | a suspended profile cannot publish (409) | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: published and not suspended is public, drafts and suspended are not | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: another user cannot change or add to a provider; domain-only columns are closed | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: set_provider_* touch only the caller's own profile | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: documents are private and the verdict is staff-only | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | offerableServiceIds: services whose required documents are all approved | Web | Passed
Staff check | require-staff.int.spec.ts | an active admin passes | Web | Passed
Staff check | require-staff.int.spec.ts | a suspended admin gets 403 | Web | Passed
Staff check | require-staff.int.spec.ts | an expired suspension no longer blocks | Web | Passed
Row-level security | rls-providers.int.spec.ts | another user cannot update or delete a service or a reference (rowCount 0, rows unchanged) | Web | Passed
Row-level security | rls-providers.int.spec.ts | another user cannot insert a service or a reference for my provider | Web | Passed
Row-level security | rls-providers.int.spec.ts | the owner cannot move a service to another provider | Web | Passed
Row-level security | rls-providers.int.spec.ts | offerableServiceIds and missingRequirements are identical through tx and the owner db | Web | Passed
Row-level security | rls-providers.int.spec.ts | a stranger asking about a draft provider gets empty answers; the owner still gets the full ones | Web | Passed
Row-level security | rls-providers.int.spec.ts | slugify strips accents | Web | Passed
Row-level security | rls.int.spec.ts | app_user cannot read a private table row of another user | Web | Passed
Row-level security | rls.int.spec.ts | public reference tables are readable by app_user and not writable | Web | Passed
Search | search.int.spec.ts | radius edge and remote providers | Web | Passed
Search | search.int.spec.ts | a remote provider more than 200 km away is found, without a distance | Web | Passed
Search | search.int.spec.ts | a draft is invisible to its owner too | Web | Passed
Search | search.int.spec.ts | distance is whole km, at least 1, hidden for remote providers outside the radius | Web | Passed
Search | search.int.spec.ts | a draft, a suspended or a provider without an offerable service never appears | Web | Passed
Search | search.int.spec.ts | category filter and q (public name and skills, case-insensitive) | Web | Passed
Search | search.int.spec.ts | bad input is 400: unknown postcode, bad format, unknown country, unknown language, bad page | Web | Passed
Search | search.int.spec.ts | paging: 20 per page and hasMore | Web | Passed
Seeds | seeds.int.spec.ts | categories seed is idempotent: 14 categories, both names, babysitting needs a police certificate | Web | Passed
Seeds | seeds.int.spec.ts | postcode import upserts: a second run leaves the same count | Web | Passed
Seeds | seeds.int.spec.ts | the dev guard needs the dev branch AND the dev database host | Web | Passed
Seeds | seeds.int.spec.ts | seedTestUsers itself refuses outside dev, before touching anything | Web | Passed
Seeds | seeds.int.spec.ts | builds the test users through the domain: published providers with photo, services, public names, verified; a rerun adds nothing | Web | Passed
Seeds | seeds.int.spec.ts | a run that crashed after the services (no photo, not published) resumes without adding the services twice | Web | Passed
Seeds | seeds.int.spec.ts | placeholder photos: gives a published profile without a photo one; elsewhere needs the typed yes | Web | Passed
Seeds | seeds.int.spec.ts | neonAuth retries a 429, then succeeds | Web | Passed
Seeds | seeds.int.spec.ts | neonAuth signs in when the email already exists | Web | Passed
Seeds | seeds.int.spec.ts | neonAuth surfaces any other sign-up failure without falling back to sign-in | Web | Passed
Services and references | services-references.int.spec.ts | a service needs a profile first (409) | Web | Passed
Services and references | services-references.int.spec.ts | create, list and patch a service; shapes fit the contract | Web | Passed
Services and references | services-references.int.spec.ts | on-request has no price, even when one is sent | Web | Passed
Services and references | services-references.int.spec.ts | bad service input: no price, three decimals, unknown category are 400 | Web | Passed
Services and references | services-references.int.spec.ts | a service in a category with required documents waits for approval | Web | Passed
Services and references | services-references.int.spec.ts | user A cannot edit or delete user B's service | Web | Passed
Services and references | services-references.int.spec.ts | references are capped at 2 (409), can be patched and deleted | Web | Passed
Sitemaps | sitemaps.int.spec.ts | providers sitemap lists only visible providers | Web | Passed
Sitemaps | sitemaps.int.spec.ts | pages sitemap lists the home page and published pages only | Web | Passed
Sitemaps | sitemaps.int.spec.ts | robots.txt allows the site, keeps the admin out and points at both sitemaps | Web | Passed
Smoke test | smoke.int.spec.ts | connects to the test database and sees PostGIS | Web | Passed
Test database guard | test-guard.int.spec.ts | the test guard refuses a non-local or non-test URL | Web | Passed
Translate | translate.int.spec.ts | stores translations and serves the second request from the store without a call | Web | Passed
Translate | translate.int.spec.ts | an edited text is re-translated, the rest comes from the store | Web | Passed
Translate | translate.int.spec.ts | texts already in the target language are returned unchanged without a call | Web | Passed
Translate | translate.int.spec.ts | a malformed or incomplete model answer stores nothing and throws TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | a non-2xx answer throws TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | line breaks survive | Web | Passed
Translate | translate.int.spec.ts | no key -> TranslationUnavailable without a call | Web | Passed
Translate | translate.int.spec.ts | the 31st AI call within an hour for one client key -> TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | the limit boundary: the 30th call passes, the 31st is refused | Web | Passed
Translate | translate.int.spec.ts | a timeout -> TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | concurrent translations of the same page store one row per text | Web | Passed
Translate | translate.int.spec.ts | writes through the request transaction and commits with it | Web | Passed
Translate | translate.int.spec.ts | the default timeout is 12 seconds | Web | Passed
Translate | translate.int.spec.ts | French and Afrikaans texts are flagged and sent to the model, in either viewer language | Web | Passed
Translate | translate.int.spec.ts | a page the detector cannot classify is translated when long enough, left alone when short | Web | Passed
Translate | translate.int.spec.ts | a German profile of short skills and titles needs no translation for de but does for en | Web | Passed
Translate | translate.int.spec.ts | a Markdown-fenced answer parses; the request carries max_tokens | Web | Passed
Translate | translate.int.spec.ts | an empty string from the model stores nothing | Web | Passed
Translate | translate.int.spec.ts | counter rows older than 24 hours are deleted; recent ones stay | Web | Passed
Translate | translate.int.spec.ts | anonymous client keys are salted hashes, never the raw IP | Web | Passed
Translate | translate.int.spec.ts | textsOf picks the translatable fields of a profile | Web | Passed
Translate | translate.int.spec.ts | needsTranslation is false for a page entirely in the viewer language and true for a mixed page | Web | Passed
Translate | translate.int.spec.ts | anonymous callers can insert and read, never update or delete | Web | Passed
Phone app | auth.test.ts | signUp posts email, password and name and stores the session cookie | App | Passed
Phone app | auth.test.ts | signIn posts email and password and returns the user | App | Passed
Phone app | auth.test.ts | a refused sign-in throws the server code, which maps to a catalogue message | App | Passed
Phone app | auth.test.ts | signOut forgets the session at once and tells the server with the old cookie | App | Passed
Phone app | auth.test.ts | signOut offline still signs out | App | Passed
Phone app | auth.test.ts | session reads get-session with the cookie; no cookie means null without a request | App | Passed
Phone app | auth.test.ts | session throws on a network error (the app offers a retry, not the login) | App | Passed
Phone app | auth.test.ts | sendVerificationCode asks for an email-verification code | App | Passed
Phone app | auth.test.ts | verifyEmail sends the code as otp, stores the new session and returns the user | App | Passed
Phone app | auth.test.ts | requestPasswordReset asks for a reset code | App | Passed
Phone app | auth.test.ts | resetPassword sends email, code and the new password | App | Passed
Phone app | auth.test.ts | a wrong code throws INVALID_OTP, shown as the code message | App | Passed
Phone app | auth.test.ts | updateUserName changes the name on the auth account | App | Passed
Phone app | auth.test.ts | signUp and signIn start without an old stored session | App | Passed
Phone app | client.test.ts | sends the stored cookie and stores a new set-cookie | App | Passed
Phone app | client.test.ts | a single joined set-cookie header (no getSetCookie) is split into its cookies | App | Passed
Phone app | client.test.ts | clears the session on 401 | App | Passed
Phone app | client.test.ts | a 401 without a stored session does not call onUnauthorized | App | Passed
Phone app | client.test.ts | every request names the app origin and leaves the platform cookie store out | App | Passed
Phone app | client.test.ts | a 409 with error and missing throws ApiError with code and missing | App | Passed
Phone app | client.test.ts | a 400 "Invalid input" lists the fields named by its issues | App | Passed
Phone app | client.test.ts | a network failure throws ApiError(0, network) | App | Passed
Phone app | client.test.ts | a server that never answers fails as network after the time limit | App | Passed
Phone app | client.test.ts | saves have no time limit: a slow save that succeeds is not reported as a failure | App | Passed
Phone app | client.test.ts | updateMe PATCHes the account name | App | Passed
Phone app | client.test.ts | upload sends multipart with the cookie and no time limit | App | Passed
Phone app | client.test.ts | upload sends the file bytes with its name and type, not a bare { uri } object | App | Passed
Phone app | client.test.ts | a file the phone cannot open is "File unreadable", not a network error, and nothing is sent | App | Passed
Phone app | client.test.ts | upload maps a 413 to ApiError "File too large" | App | Passed
Phone app | client.test.ts | upload maps a network failure to ApiError network and does not retry | App | Passed
Phone app | client.test.ts | a store that cannot be read (Keystore failure) sends the request without a cookie | App | Passed
Phone app | client.test.ts | a cookie that cannot be saved does not fail a request the server already carried out | App | Passed
Phone app | client.test.ts | a malformed Set-Cookie line without "=" is skipped | App | Passed
Phone app | my-profile.test.ts | a failed check after the upload deletes the uploaded file and reports the original error | App | Passed
Phone app | my-profile.test.ts | a successful submit deletes nothing | App | Passed
Phone app | my-profile.test.ts | a failing clean-up does not hide the original error | App | Passed
Phone app | use-session.test.ts | loading -> signed in -> signed out | App | Passed
Phone app | use-session.test.ts | an unverified email never counts as signed in: sign-in sends a code and asks for it | App | Passed
Phone app | use-session.test.ts | a server that refuses unverified sign-ins (EMAIL_NOT_VERIFIED) also leads to the code screen | App | Passed
Phone app | use-session.test.ts | sign-up creates the account and sends the code; the right code signs in and saves the account name | App | Passed
Phone app | use-session.test.ts | a wrong code throws and keeps signed out | App | Passed
Phone app | use-session.test.ts | a failed login rejects and keeps signed out; a server error on load means signed out | App | Passed
Phone app | use-session.test.ts | a network error on load sets offline (not signed out); retry recovers | App | Passed
Phone app | use-session.test.ts | onUnauthorized from the API client signs the user out | App | Passed
Phone app | use-session.test.ts | updateName saves the account name in both places and updates the session user; a failure keeps the old one | App | Passed
Phone app | use-session.test.ts | switching the language also saves it for emails, but only while signed in | App | Passed
Phone app | index.test.ts | texts come from the shared catalogue, in the chosen language, with placeholders filled | App | Passed
Phone app | index.test.ts | the translate button texts exist in both languages | App | Passed
Phone app | index.test.ts | errorText maps the auth server codes to catalogue messages | App | Passed
Phone app | index.test.ts | errorText maps the app API strings | App | Passed
Phone app | index.test.ts | docText maps known document codes and passes unknown ones through | App | Passed
Phone app | documents.test.ts | no rows when no service needs a document | App | Passed
Phone app | documents.test.ts | a babysitting service with nothing uploaded → police-certificate none | App | Passed
Phone app | documents.test.ts | the most recently reviewed check decides, like the server | App | Passed
Phone app | documents.test.ts | a pending check shows pending even after an approval | App | Passed
Phone app | documents.test.ts | a requirement code the app does not know still gets a row, after the known ones | App | Passed
Phone app | documents.test.ts | two services needing the same document give one row | App | Passed
Phone app | documents.test.ts | a hidden service says a document is needed until it is uploaded, then that it waits for the check | App | Passed
Phone app | format.test.ts | prices follow the website rules in German and English | App | Passed
Phone app | format.test.ts | distance shows km, remote or nothing | App | Passed
Phone app | format.test.ts | search path leaves out empty filters and trims text | App | Passed
Phone app | format.test.ts | photoSrc loads only absolute http(s) URLs, never a server-relative /api path | App | Passed
Phone app | match.test.ts | matches ignores case and accents, and an empty query matches everything | App | Passed
Phone app | pick.test.ts | preparePhoto keeps the long side at 1600 px | App | Passed
Phone app | pick.test.ts | tooLarge is true above 4_434_464 bytes | App | Passed
Phone app | pick.test.ts | cancelled is null | App | Passed
Phone app | pick.test.ts | a refused permission is denied, not cancelled | App | Passed
Phone app | pick.test.ts | offers PDFs and the image types the server accepts, from any file source | App | Passed
Phone app | pick.test.ts | cancelled is null | App | Passed
Phone app | profile-form.test.ts | profile validation mirrors the server limits | App | Passed
Phone app | profile-form.test.ts | profile body clears empty fields and drops business fields for private providers | App | Passed
Phone app | profile-form.test.ts | the account name is not part of the profile body; the form pre-fills it from the session user | App | Passed
Phone app | profile-form.test.ts | server errors land on the right field | App | Passed
Phone app | profile-form.test.ts | withItem adds a trimmed new skill or strength once and ignores blanks | App | Passed
Phone app | profile-form.test.ts | strengths are a list in the form and one per line on the server | App | Passed
Phone app | profile-form.test.ts | the form-level error shows unless every server error has an inline slot | App | Passed
Phone app | profile-form.test.ts | service and reference validation | App | Passed
Phone app | profile-form.test.ts | every missing item the publish route can return has de and en text | App | Passed
Phone app | profile-form.test.ts | the service body names the category by id and the currency, as the server expects | App | Passed
Phone app | profile-form.test.ts | a 400 "Invalid input" marks each named field | App | Passed
Phone app | translation.test.ts | applyTexts swaps only the translatable fields and keeps names, prices and photos | App | Passed
Phone app | translation.test.ts | applyTexts matches services and references by id and leaves unknown ones untouched | App | Passed
Phone app | translation.test.ts | applyTexts keeps line breaks | App | Passed
Phone app | auth-layout.test.ts | logged-out landing route is login | App | Passed
Phone app | auth-layout.test.ts | no test files inside src/app (each file there becomes a screen) | App | Passed
Shared packages | contract/index.test.ts | rejects three decimals and negative prices | Packages | Passed
Shared packages | contract/index.test.ts | needs no price on request | Packages | Passed
Shared packages | contract/index.test.ts | caps pageSize at 100 | Packages | Passed
Shared packages | contract/index.test.ts | parseBody answers 400 with the issues | Packages | Passed
Shared packages | contract/index.test.ts | parseQuery reads the search params | Packages | Passed
Shared packages | contract/index.test.ts | lists are { docs: [...] } | Packages | Passed
Shared packages | contract/index.test.ts | reference year is checked against the current year at parse time | Packages | Passed
Shared packages | i18n/index.test.ts | de and en have the same keys | Packages | Passed
Shared packages | i18n/index.test.ts | no text is empty and no two keys of one namespace carry the same text | Packages | Passed
Shared packages | i18n/index.test.ts | no text contains Treuhand, Escrow, garantiert or a competitor name | Packages | Passed
Shared packages | i18n/index.test.ts | the product name is only written in brand.name | Packages | Passed
Shared packages | i18n/index.test.ts | replaces placeholders and falls back to the key when missing | Packages | Passed
Shared packages | i18n/index.test.ts | fills the brand name without a parameter | Packages | Passed
Shared packages | i18n/index.test.ts | knows its languages | Packages | Passed
Shared packages | i18n/index.test.ts | formats per language | Packages | Passed
Shared packages | i18n/index.test.ts | formats price labels from the catalogue | Packages | Passed
Seeds | seeds.int.spec.ts | loadSeedData reads the git-ignored list or the committed example, and rejects a broken file | Web | Passed

## Other Checks
Check | What it tested | Outcome | Notes
pnpm typecheck | All packages and apps compile with no type errors. | Passed | Run 27 October.
pnpm lint | ESLint over the whole repository. | Passed | Run 27 October.
cd apps/mobile && npx tsc --noEmit | App code compiles. | Passed | Run 27 October.
Web integration tests on the Docker database | 32 spec files against local Postgres 17 + PostGIS (port 5433). | Passed | 204 tests (203 at the final fix wave; one seed-data test added 27 October).
Parity: sign-up with code | Account creation with an email code (app). | Not yet done (phone) | Evidence: apps/mobile/src/api/auth.test.ts, hooks/use-session.test.ts (client calls and flow, server mocked) and apps/web/tests/auth-cookie-flow.int.spec.ts (real sign-up and cookie). The emailed code and the screens need a phone run.
Parity: login | Login with email and password (app). | Passed | Evidence: apps/mobile/src/api/auth.test.ts, hooks/use-session.test.ts; apps/web/tests/auth-cookie-flow.int.spec.ts (a real sign-up cookie reaches /app-api/v1/me, which answers 403 until the email is confirmed). Screens still need a phone run.
Parity: 7-day session | Login stays valid for 7 days. | Not yet done (phone) | The length is a Neon Auth setting; no test reads it. Check on the dev build over several days.
Parity: password reset by code | Reset the password with an emailed code (app). | Not yet done (phone) | Evidence for the client calls: apps/mobile/src/api/auth.test.ts (server mocked). The real code email needs a phone run.
Parity: home (app) | Home tab with categories. | Not yet done (phone) | Built (apps/mobile/src/screens/home); categories endpoint tested in apps/web/tests/categories.int.spec.ts; screen not tested.
Parity: search | Search by category and postcode. | Passed | Evidence: apps/web/tests/search.int.spec.ts (radius, remote, hidden providers, paging, bad input). The app screen needs a phone run.
Parity: provider screen | Provider screen in the app. | Passed | Evidence: apps/web/tests/provider-public.int.spec.ts and public-name.int.spec.ts (data). Screen layout needs a phone run.
Parity: translate | Translate provider texts into German or English (app and website). | Passed | Evidence: apps/web/tests/translate.int.spec.ts, provider-translation.int.spec.ts, provider-page.int.spec.ts; apps/mobile/src/lib/translation.test.ts.
Parity: my profile with services | Create and edit own profile and services. | Passed | Evidence: apps/web/tests/provider-profile.int.spec.ts, services-references.int.spec.ts; apps/mobile/src/api/my-profile.test.ts, lib/profile-form.test.ts.
Parity: references | Up to 2 references per profile. | Passed | Evidence: apps/web/tests/services-references.int.spec.ts.
Parity: photos | Profile photo and portfolio photos. | Passed | Evidence: apps/web/tests/files.int.spec.ts, files-review.int.spec.ts; apps/mobile/src/lib/pick.test.ts. Camera and library pickers need a phone run.
Parity: documents | Upload verification documents (PDF, or a JPEG, PNG or WEBP scan or photo) and see their status. | Passed | Evidence: apps/web/tests/files.int.spec.ts (PDF, JPEG, PNG and WEBP accepted and stored with their own type; GIF and text refused; staff link to an image document), files-review.int.spec.ts; apps/mobile/src/lib/documents.test.ts. Fixed in the final fix wave: images were refused before (only PDF). Scan, gallery and OneDrive picking need a phone run.
Parity: publish and unpublish | Live switch; publishing needs a photo and a service. | Passed | Evidence: apps/web/tests/publish-flow.int.spec.ts.
Parity: admin document review | Staff approve or reject documents; email to the user. | Passed | Evidence: apps/web/tests/admin-api.int.spec.ts, email.int.spec.ts. The Refine screens need a browser run.
Parity: admin users | List, filter and suspend users. | Passed | Evidence: apps/web/tests/admin-api.int.spec.ts. Screens need a browser run.
Parity: admin categories | Create and edit categories per language. | Passed | Evidence: apps/web/tests/admin-api.int.spec.ts, categories.int.spec.ts. Screens need a browser run.
Parity: admin pages | Create and publish pages. | Passed | Evidence: apps/web/tests/admin-api.int.spec.ts, pages.int.spec.ts. Screens need a browser run.
Parity: staff roles | Administrator and Reviewer. | Passed | Evidence: apps/web/tests/admin-roles.int.spec.ts, require-staff.int.spec.ts.
Parity: website home | Home page in German and English. | Passed | Evidence: apps/web/tests/home-page.int.spec.ts. Look and feel needs a browser run.
Parity: provider page (website) | Public provider page. | Passed | Evidence: apps/web/tests/provider-page.int.spec.ts.
Parity: legal pages | Impressum, Datenschutz, AGB, Ranking as pages. | Passed | Evidence: apps/web/tests/pages.int.spec.ts (pages work). The texts themselves are still to be written by staff (see Open Items).
Parity: sitemaps | providers and pages sitemaps, robots.txt. | Passed | Evidence: apps/web/tests/sitemaps.int.spec.ts.

## Open Items
Item | Detail | When
Phone checks of every screen | Every app screen on the development build against a preview deployment, and the Refine admin screens in a browser. No phone or browser run happened for Stage 1. | Owner, next
Vercel project for KANDO | Does not exist yet. Steps in docs/deployment.md. | Owner
CI secrets | Optional: without NEON_AUTH_BASE_URL and NEON_AUTH_COOKIE_SECRET the one test against the real Neon Auth is skipped in CI. CI is green without them. | Owner, optional
Final whole-branch review | Done (final-review.md): 0 Critical, 3 Important, 10 Minor. All Important and 8 Minor fixed in the final fix wave (commits 65be850 to d68d4d0); the other 2 Minor are deferred to the South Africa work (see README Known gaps). | Fixed
Seed guard uses ?? for NEON_DEV_ENDPOINT_ID | Fixed in ebfccdd: an empty value now falls back to the dev endpoint (seeds.int.spec.ts checks it). | Fixed
Seed resume after a crashed photo upload | Fixed in d68d4d0: a provider that already has services skips adding them again (seeds.int.spec.ts checks it). | Fixed
postcodes.int.spec.ts flaky once | Fixed in d68d4d0: the import test now has 30 seconds. | Fixed
No thumbnail sizes | Photo grid and cards load full-size images. | Backlog
Documents over 4.5 MB | Cannot be uploaded through Vercel (body limit); upload straight from the phone to storage later. | Backlog
No Delete my account | GDPR erasure and data export are planned for a later stage. | Later stage
No security scan yet | Row-level security, Next.js routes and Vercel settings, before launch. | Before launch
Placeholder graphics | App icon, splash and home page pictures. | Before launch
Legal pages are staff-created records | Impressum, Datenschutz, AGB and Ranking pages must be written and published in the back office. | Before launch
Vercel Pro plan | Hobby is not allowed for commercial use. | Before launch
Final review I-1: suspension bypass | A user suspended before having a profile could create one and publish it. Fixed in 65be850 (function set_provider_published in packages/db/src/rls.ts; admin-api.int.spec.ts). | Fixed
Final review I-2: unconfirmed emails | The app API now refuses accounts whose email is not confirmed (403). Fixed in 70403fb (provider-profile, app-request and auth-cookie-flow specs). | Fixed
Final review I-3: image documents | JPEG, PNG and WEBP documents are accepted next to PDF, cleaned of metadata. Fixed in 7b7c342 (files.int.spec.ts). | Fixed
Final review M-1: two-language switches | Language lookups use the language list and the default language. Fixed in 39055cc. | Fixed
Final review M-2: fixed currency and postcode length | Currency read from the service; postcode length left to the country lookup. Fixed in 172c21a. | Fixed
Final review M-3: empty account name | Slug falls back to the display name; the first contact copies the account name. Fixed in 4a7e9d7 (public-name.int.spec.ts). | Fixed
Final review M-4: empty DATABASE_URL_UNPOOLED | Migrations, imports and seeds fall back to DATABASE_URL. Fixed in ebfccdd. | Fixed
Final review M-5: email outbox in production | Without RESEND_API_KEY one log line, no text, nothing kept. Fixed in 56ee8e3 (email.int.spec.ts). | Fixed
Final review M-6: seeds section of the deployment notes | Corrected, including ALLOW_PRODUCTION=1 at cutover. Fixed in the docs commit of the final fix wave. | Fixed
Final review M-7: PATCH /me body check | Checked with MePatchSchema from the contract. Fixed in fdd6ba2 (provider-profile.int.spec.ts). | Fixed
Final review M-8: eligibility for hidden providers | Answers only for a visible provider or the caller's own. Fixed in 65be850 (rls-providers.int.spec.ts). | Fixed
Final review M-9 and M-10: German legal links, two-language switch on the website | Footer legal links and the website language switch assume Germany and two languages. Deferred to the South Africa work. | South Africa work
CI: categories seed test failed on GitHub | Counted all categories; other spec files leave their own behind in the shared CI database. Counts only the seeded slugs now. Fixed in 67c80bb; CI green since. | Fixed
Seed account list out of git (owner request, 27 October) | The 14 test accounts, their password and made-up profiles were in packages/domain/src/seed/test-users.ts in a public repository. Now read from the git-ignored seed-data/test-users.json; a one-customer-one-provider example file is committed; tests use their own fixture. Fixed in a72cf74. Earlier commits still hold the list: squash-merge PR #2 and delete the branch. | Fixed
Code review 27 October (mobile build config), 1 of 6: microphone permission | The image-picker plugin added android.permission.RECORD_AUDIO and an iOS microphone text by default; the app never records audio. Plugin option microphonePermission=false, hand-written permissions list removed. Resolved config checked: no microphone entry. Fixed in 27ea70c. | Fixed
Code review 27 October, 2 of 6: production API address | The production build profile did not pin EXPO_PUBLIC_API_URL, so a local build could bake in a LAN address. Pinned to https://skillweb.space like the preview profile. Fixed in 27ea70c. | Fixed
Code review 27 October, 3 to 5 of 6: dead configuration | Empty ios.infoPlist, the router asyncRoutes block the plugin overwrites, and the empty submit.production placeholder removed. Fixed in 27ea70c. | Fixed
Code review 27 October, 6 of 6: README duplication | Concerns the old skill-web README only (development-build status repeated in two places). Not applicable to KANDO. | Not applicable