## Summary
Topic | Detail
Purpose | Everything that must still be done before KANDO: SkillWeb can be released as an MVP and assessed against the capstone criteria. Written 1 November 2026 from the README, the plans, the review reports, the open pull requests, the memory notes and the state of the repository. Sorted by importance on the Tasks sheet.
Latest update (1 November 2026, later) | Owner decisions recorded: Neon approved; the AI feature uses an OpenRouter model, covers all documents including photo ID (sensitive data protected), automatic decisions are allowed with a human check in some cases, and the AI quote assistant is to be discussed when AI planning starts. The agents, commands and skills used in the project were added to the project .claude folder (branch chore/claude-folder, PR to be opened). The review finding was corrected: reviews were done and written up, but none is recorded on GitHub. preferredDate was removed completely (database column, contract, server, export, app form and display, texts; migration 0027) because nobody uses the app; a scan found no other unused table or column (currencies.minor_units is kept for other currencies). A reuse map for the app screens was proposed (no new fields; the old preferredDate and accept screen fall away) and awaits the owner's confirmation. Reminders are saved (see the Reminders sheet).
Where the project stands | A large, working product: Expo phone app, Next.js website and back office on Vercel (https://skillweb.space), Neon Postgres with row-level security, Stripe Connect in TEST mode, invoices, chat, disputes, reviews, 4 cron jobs, German and English texts, 140+ commits, 47 pull requests, thousands of automated tests. Flow 1 (one request-to-booked flow with a quote document) is half built: the server side, the quote PDF, numbering and lists are done (PR #47, open, not merged); the app screens are not.
The four things that decide the assessment | 1. AI feature: the capstone cases are AI cases. The app has one small AI feature (the Translate button via OpenRouter). The planned AI document check is not built. 2. Agentic-engineering evidence: there is still no CLAUDE.md. The used agents, commands and skills are now in the project .claude folder (branch chore/claude-folder, not merged yet). Reviews were done in sessions and written up in Reports/, but GitHub records none: use /code-review --comment and a GitHub review before the next merge. 3. Stack match: the criteria name Supabase; the project uses Neon (Postgres, row-level security, Neon Auth). APPROVED by the owner on 1 November 2026; only the short evidence note remains. 4. A working live URL with the finished flow: the live site is behind the code (production runs the 31 October release), PR #47 must not go live before the app screens exist (see the release warning below), and the phone walk-through and a Stripe test payment have not been done by a person.
RELEASE WARNING (act on this) | PR #47 makes the server require a date and time on every new request (400 time-required without one). The current phone app and the production APK send requests without a time. If #47 is merged and deployed before Tasks 10 to 12 (the app screens), every new request from the existing app fails. Also: migrations 0024 to 0026 must be applied to the production database (kando-main) BEFORE the code that needs them is deployed (README rule). Recommended: keep #47 open until the app screens are ready, then merge and release together.
Recommended order of work | Phase 1 (finish the product): Flow 1 Tasks 9 to 13, owner decisions that block it, merge and release with migrations, phone walk-through. Phase 2 (the AI feature): decide the provider, build the AI document check with disclosure. Phase 3 (assessment evidence): CLAUDE.md, a project skill/command/subagent, a reviewed PR, security scan and fixes, README paragraph, GDPR and Article 50 checks. Phase 4 (presentation): demo accounts, deck in the SCR frame, showcase upload, rehearsal.
Not needed for the capstone | App Store and Google Play submission, real payments (live Stripe keys), the lawyer and tax answers for real money, Flow 2 (availability and instant booking) and the post-launch feature list. They stay documented so nothing is lost, but they are marked Low or Medium on the Tasks sheet. The capstone accepts a phone or emulator build; Android works today (iPhone needs a paid Apple Developer account).
Effort scale | S = up to half a day, M = one to two days, L = three days or more (one working session of Claude Code plus owner input where stated). Who: Claude = can be built or written in a session; Owner = a decision, a dashboard action or a real-world step only the owner can do; Both = needs the owner's input first.
Sheets | Plan (the order to get everything done, phase by phase) ¦ Tasks (sorted by importance) ¦ Capstone scorecard ¦ Owner decisions ¦ Owner actions ¦ Reminders ¦ Reuse map (app screens and fields).

## Plan
Step | Phase | What happens | Done when | Needs first | Who | Effort | Tasks sheet No | Can run alongside | Status
0.1 | 0 Decide and set up | Hold PR #47 (do not merge): the server now requires a date and time on requests and the current app cannot send one. | PR #47 stays open until step 1.9. | - | Owner | S | 4 | everything | In progress
0.2 | 0 Decide and set up | AI feature planning: the owner decisions are in (OpenRouter model; all documents including photo ID, sensitive data protected; automatic decisions with a human check in some cases). Still to settle in the plan: the human-check rule, how ID data is protected, the model, cost cap, and the AI quote assistant (owner asked to be reminded). Result: a written plan in docs/superpowers/plans/. | AI plan approved by the owner. | - | Both | S | 2 | 0.3, 1.1 | Done
0.3 | 0 Decide and set up | PARTLY DONE: the .claude folder with the used agents, commands and skills and its README is on branch chore/claude-folder (open the PR, review it with /code-review --comment, owner approves on GitHub, merge). Still to do: CLAUDE.md in the root, the /test-report command, the RLS-check agent, and a README section "How this project is built with Claude Code". | CLAUDE.md in the root; .claude merged to main; README section added. | - | Both | S | 5, 6, 7 | 0.2, 1.1 | Waiting for owner
0.4 | 0 Decide and set up | Write the one-page RLS and auth evidence note (Neon approved by the owner). | docs/rls-and-auth-evidence.md. | - | Claude | S | 1 | 0.2, 1.1 | Waiting for owner
0.5 | 0 Decide and set up | Confirm the reuse map for the app screens (Reuse map sheet); update Tasks 10 to 12 of the Flow 1 plan as a reuse map (plan text only). Note: the approved plan retires direct booking (the Book button opens the same request form), so the earlier suggestion to keep it until Flow 2 was dropped. | Owner confirmation; plan updated. | - | Owner | S | 3, 17, 28 | 0.2, 0.3 | Done
0.6 | 0 Decide and set up | Post a Review record comment on each merged PR that has a written review (owner go-ahead pending). | Comments visible on the merged PRs. | owner go-ahead | Claude | S | 7 | everything | Done
1.1 | 1 Finish Flow 1 | Task 9: finish the notice wording (in-app, push, email, German and English) and correct the plan text. | Notice texts complete; i18n parity and notification specs pass. | - | Claude | S | 15 | 0.x | Waiting for owner
1.2 | 1 Finish Flow 1 | Task 10a (app): ONE request form by extracting the shared "when and where" fields from TimeProposalForm (date, time, duration, on site, address prefilled from the saved account address, note) with native date and time pickers (Finding 2); (the old preferredDate field is already removed). The same shared fields serve the enter-a-time and counter screens. | A customer can send a request with a time on a phone build; jest tests for the form. | 1.1 | Claude | M | 3, 20 |  | Done
1.3 | 1 Finish Flow 1 | Task 10b (app): provider answer panel by extending the existing SendQuoteForm (amount, scope, optional date, time, duration) with the switch "date and time confirmed", prefilled with the request's time; propose another time; reject (decline already exists). | Provider can answer every request type; jest tests. | 1.2 | Claude | M | 3 |  | Done
1.4 | 1 Finish Flow 1 | Task 10c (app): customer quote screen by extending the existing QuoteCard and request page: Confirm (replaces the accept screen, which falls away); Decline with the offer to chat first; find another provider; pending-time confirm button; awaiting-time status text; no stand-in time shown; "discuss changes in the chat" instead of an edit button once a quote exists. | The whole flow can be walked in the app; jest tests. | 1.3 | Claude | M | 3 |  | Done
1.5 | 1 Finish Flow 1 | Task 11 (app): "Quotes sent" and "My received quotes" on the account page, PDF open / download / print. | Both lists and the PDF open on a phone build. | 1.4 | Claude | M | 16 | 1.6 | Done
1.6 | 1 Finish Flow 1 | Task 12: retire the old proposed-booking path for quotes, make the time required in the contract, remove the AcceptQuoteScreen route (preferredDate is already gone), keep accept only for additional tasks; The Book button opens the same request form; POST /bookings and BookScreen retire (instant booking returns with Flow 2). | No second booking path; specs updated. | 1.4 | Claude | M | 17 | 1.5 | Open
1.7 | 1 Finish Flow 1 | Task 13: full suites once, test report in Reports/, README update, phone test script with a tap count before and after. | Reports/Flow-1-Test-Report.xlsx; all suites green. | 1.5, 1.6 | Claude | M | 18 |  | Open
1.8 | 1 Finish Flow 1 | Decide the open Flow 1 points (street privacy, second PDF, PDF language) and apply the answers. | Decisions recorded in the plan. | - | Owner | S | 19 | 1.2-1.7 | Open
1.9 | 1 Finish Flow 1 | Release: apply migrations 0024 to 0026 to kando-main, merge #47 and the app PR, check production, make a new Android build. | Production runs Flow 1; new APK installed on the test phone. | 1.7, 1.8, owner actions O.1 | Both | M | 4, 34 |  | Open
1.10 | 1 Finish Flow 1 | Phone walk-through on Android with the test accounts, including a full Stripe TEST payment; fix what it finds; retest findings 4 and 6. | Walk-through list signed off by the owner; fixes merged. | 1.9 | Both | M | 12, 20 |  | Open
2.1 | 2 AI feature | Provider and data protection: choose the provider, sign the processing agreement, sign off the DPIA, add the key to Vercel (server side only). | Provider contract and DPIA sign-off recorded in docs/legal-drafts. | 0.2 | Owner | S | 2, 25 | Phase 1 | Open
2.2 | 2 AI feature | Build the backend: table with row-level security for AI results, server job after upload, model call through the provider, result stored as a suggestion, rate limits and cost cap, tests (incl. a failing provider). | Upload creates a suggestion; failures never block an upload; specs pass. | 2.1, 0.2 | Claude | L | 2 |  | Open
2.3 | 2 AI feature | Back office: a suggestion panel next to each document (type, name match, expiry, flags), staff decide as before; the decision is logged. | Reviewer sees suggestion and decides; admin specs pass. | 2.2 | Claude | M | 2 |  | Open
2.4 | 2 AI feature | Disclosure and privacy: label in German and English where the person uploads and where staff see the suggestion; privacy text names the provider; the Article 50 note. | Labels visible; docs/article-50-note.md. | 2.3 | Claude | S | 10 |  | Open
2.5 | 2 AI feature | Delete my data covers the AI result; export contains it. | Deletion spec proves removal. | 2.2 | Claude | S | 11 | 2.3 | Open
2.6 | 2 AI feature | Evaluation: run the feature on about 20 sample documents (made-up documents, never real ones), compare with the staff decision, record the result. | A measured result (for example 18 of 20 correct) in Reports/. | 2.3 | Both | S | 26 |  | Open
3.1 | 3 Security and compliance | Run the security scan on the final code (/security-scan and the three scanners); fix every critical and high finding and the open items (anonymous inserts into translations, owner_id readable, whole-row admin detail, server-only, CSP script-src). | docs/security-scan-<date>.md: no critical or high open. | 1.7, 2.3 | Claude | M | 8 | 3.2 | Open
3.2 | 3 Security and compliance | Secrets: scan working tree and history again; clean up Vercel Preview variables; mark secrets Sensitive; WAF rate-limit rules. | Clean scan output; checklist ticked by the owner. | owner actions | Both | S | 9 | 3.1 | Open
3.3 | 3 Security and compliance | Legal pages published (Impressum, Datenschutz, AGB, Ranking) in German and English; age and terms tick at sign-up; report this profile or photo; public web page to request deletion. | Pages live; tick enforced; spec covers it. | owner supplies company details | Both | M | 24, 11 | 2.x | Open
3.4 | 3 Security and compliance | Real deletion on the live Neon Auth with a throw-away account; confirm everything is gone. | Written result in the evidence folder. | 1.9 | Both | S | 11 |  | Open
3.5 | 3 Security and compliance | Run /code-review --comment on the release PR so the review is visible on GitHub; fix; the owner submits a GitHub review (Approve) and merges. | At least one PR shows a recorded review on GitHub. | 1.7 | Both | S | 7 |  | Open
4.1 | 4 Quality and evidence | Green repository: lint errors (38) and mobile type errors (4) fixed or excluded; CI green; update README "Where we are", Known gaps and test numbers. | pnpm lint, pnpm typecheck and CI all green on main. | 1.9 | Claude | S | 23, 35 |  | Open
4.2 | 4 Quality and evidence | Demo data on production: delete the old test accounts; create one demo customer and two published demo providers with approved documents, finished jobs and reviews. | Demo walk-through works end to end on the live site. | 1.9, 2.3 | Both | S | 22 |  | Open
4.3 | 4 Quality and evidence | README top section: goal / problem / how it works paragraph, Situation-Complication-Resolution, stack, AI disclosure; re-check the scorecard sheet. | Every row of the scorecard is Met. | all above | Claude | S | 13 |  | Open
5.1 | 5 Presentation | Deck in the SCR frame with the six points; screenshots and a recorded demo as fallback; evaluation numbers from the reports. | Deck and demo script ready. | 4.3 | Both | M | 14, 26 |  | Open
5.2 | 5 Presentation | Upload the project to showcase.turingcollege.com; rehearse the 10 minutes; prepare answers for the 5 minutes of questions (stack choice, RLS, AI risk, what is next). | Showcase entry live; rehearsal done. | 5.1 | Owner | S | 14 |  | Open
O.1 | Owner actions (run in parallel from day 1) | Vercel Preview variables and plan, Stripe Preview webhooks, storage keys, Neon Auth settings, first administrator on production, Resend domain, FCM credentials (see the Owner actions sheet). | Owner actions sheet ticked. | - | Owner | M | 21, 33 | Phases 1 to 3 | Open

## Tasks
No | Priority | Area | Task | Why it matters (capstone / product) | Current state | Effort | Who | Status
1 | Critical | Capstone: stack | Confirm with the course lead (STL) that Neon [DONE: approved by the owner 1 Nov 2026; only the evidence note remains] (Postgres, row-level security, Neon Auth/Better Auth) is accepted in place of Supabase. Ask in writing and keep the answer. Prepare a one-page "RLS and auth evidence" note: every table holding user data is classified in packages/db/src/rls.ts and a check lists any table that is not; the policies, triggers and role split (app_user vs owner) are tested by the integration specs. | The criteria name "Supabase (Auth and Row Level Security)". The brief also says an own idea is valid if it meets the requirements; the requirements (auth, RLS on every user-data table, server-side secrets) are met on Neon. An unconfirmed stack difference is the largest avoidable risk. | Neon APPROVED by the owner on 1 November 2026. Remaining: the one-page evidence note (RLS and auth) for the assessor. | S | Owner asks; Claude writes the note | Waiting for owner
2 | Critical | Capstone: AI | Decide and build the capstone AI feature. Agreed direction: AI check of uploaded verification documents, ALL document types including photo ID. A vision-capable OpenRouter model (server side only) reads the uploaded document, suggests its type, name match and expiry date, and flags problems; the result is stored per document (row-level security). Automatic decisions are allowed, but a human checks some cases (rule to design: for example low confidence, every ID photo, a name mismatch, a random sample). ID data is protected: visible only to the person and staff, never logged, sent to the model only for the check, deleted with the account. Fits the existing documents flow, the planned DPIA (docs/legal-drafts/dpia-ai-document-checks-draft.md) and the "multi-modal" case. Build: server job after upload, table with RLS, back-office panel, German and English disclosure text, tests, a "delete my data" path that removes the AI result. Alternatives if the owner prefers: AI help in the chat contact check, or an AI "quote assistant" that drafts the scope text of a quote from the request. | Every capstone case is built around an AI feature, and the evaluation asks for AI disclosure (EU AI Act Article 50). Today the only AI feature is the Translate button (OpenRouter, rate limited, labelled "Automatically translated (AI)"). Without a real AI feature the project does not fit any of the seven cases well. | Owner decisions 1 Nov 2026: an OpenRouter model must be used; all documents including photo ID (the sensitive ID data must be protected); automatic decisions allowed, checked by a human in some cases; the AI quote assistant is to be discussed at AI planning (reminder saved). Not built. DPIA is a draft; EU data location, processing terms and no-training settings must still be checked for the chosen OpenRouter model. | L | Both (owner decides provider and feature; planning started 1 Nov) | In progress
3 | Critical | Product: Flow 1 | Finish Flow 1 in the app (Task 10), by REUSING the existing screens and fields (see the Reuse map sheet; owner confirmation pending): ONE request form (what, where, date and time); the provider answer panel (quote with or without a time, switch "date and time confirmed", reject); the customer quote screen (confirm, decline with the offer to chat first, find another provider); pending-time display and confirm button (pendingTime is in the contract); the awaiting-time status text and hiding the stand-in time; "discuss changes in the chat" instead of an edit button once a quote exists; date and time pickers (Finding 2). | This is the core of the product and the thing the owner asked for. The server is ready; without the screens the new flow cannot be used or shown, and the old app breaks if the server is released alone. | Server side built (Tasks 1 to 7, 6a, 6b, routes for lists and PDF); no app screens. | L | Claude | In progress
4 | Critical | Product: release | Release sequence for Flow 1: (1) finish Tasks 9 to 12; (2) apply migrations 0024 to 0026 to kando-main; (3) merge #47 (and the app PR) to main; (4) verify production; (5) build a new Android APK that points at production. Do not merge #47 earlier (see the release warning on the Summary sheet). | Merging early breaks request creation for every existing app; deploying code before the migration breaks the API. | PR #47 open, CI green, migrations applied to the dev database only. | M | Owner merges; Claude prepares | Open
5 | Critical | Capstone: agentic practice | Add a CLAUDE.md to the project root (project rules: owner merges, no AI co-author lines, German and English for every text, tests per task and full suites at stage end, reports in Reports/, no competitor names, South Africa later) and keep the README "How a new session starts" in sync. | The criteria ask for a CLAUDE.md. None exists; the rules live only in the README and in private memory files. | Missing. | S | Claude | Waiting for owner
6 | Critical | Capstone: agentic practice | Save at least one project skill, slash command or subagent in the repo (.claude/commands or .claude/agents; the folder is empty today) and document in the README how it was used. Suggested: a /test-report command (builds the Reports/ Excel from the test output), a pr-review subagent (the code-review pass that was run on PR #47), an rls-check subagent (lists tables without policies). Use each at least once and keep the output. | The criteria ask for evidence of skills, slash commands or subagents. Many were used in sessions (code-review, security scanners, research and review subagents), but nothing is saved in the project that an assessor could open. | PARTLY DONE 1 Nov 2026: the verified agents (ai-architect, ai-researcher, ai-code-reviewer, nextjs- and vercel-security-scanner), the commands security-scan and security-scan-changed and the skills brainstorming, writing-plans, subagent-driven-development and neon-postgres are copied into the project .claude folder with a README (branch chore/claude-folder, commit ed55d72, PR to open). Still to add: a /test-report command and an RLS-check agent, and use each once. | S | Claude | Waiting for owner
7 | Critical | Capstone: agentic practice | Have at least one pull request reviewed before it is merged, visibly on GitHub: run /code-review --comment on the next PR (inline comments), fix the findings, then the owner submits a GitHub review (Approve) and merges. Good first candidate: the .claude folder PR. In addition, post a "Review record" comment on each merged PR that has a written review (14 to 16, 18 to 20, 46, 47, the assessment-fix PRs) with the findings and fixes; owner go-ahead pending (comments post under the owner GitHub account; nothing is invented for PRs without a written review). Reminder saved for every merge. | The criteria ask for "at least one pull request reviewed before merging". GitHub currently shows no formal review on any of the 47 PRs; the reviews exist as reports and my own checks, which an assessor will not see on GitHub. | Reviews were done in Claude Code sessions and written up as Excel reports (PRs 14-16, 18-20, 46-47, assessment stages), but none is recorded ON GitHub (the API shows 0 reviews on 47 PRs; the 42 PRs with comments are mostly the Vercel bot). An assessor looking at GitHub sees no review. | S | Both | In progress
8 | Critical | Capstone: security | Run the /security-scan (or /security-scan-changed on the branch) again on the final code and fix every critical and high finding; record the result in docs/ (the last scan, docs/security-scan-2026-10-29.md, ran on code from before the assessment fixes and Flow 1). Close the open items it lists: anonymous inserts into translations/translation_requests and the public client_key; owner_id and suspended_until readable on published providers (table-wide SELECT); admin provider detail returns the whole row; add server-only to the db client and auth server files; enforce the Content-Security-Policy script-src (check the console first); WAF rate-limit rules in Vercel. | "A /security-scan pass" is an explicit criterion. | Scanned 29 October: 0 critical, 0 high; several medium/low items open. | M | Claude (scan, code fixes); Owner (Vercel rules) | Open
9 | Critical | Capstone: security | Prove that secrets are out of the repo and server side only: re-run a secret scan over the working tree and git history (the 29 October scan found nothing), confirm .env is ignored, and finish the Vercel environment clean-up (untick Preview on live storage keys, RESEND_API_KEY, OPENROUTER_API_KEY, CRON_SECRET; give Preview its own test values; mark secrets Sensitive; Stripe key prefix check). | Explicit criterion. The code side is clean; the Vercel side needs the owner's dashboard actions. | Code: clean at the last scan. Dashboard actions: open. | S | Owner (dashboard), Claude (scan) | Open
10 | Critical | Capstone: compliance | AI disclosure (EU AI Act Article 50): list every AI output and show the label in German and English: the Translate button already says "Automatically translated (AI)"; the new AI document check needs a visible note where the person uploads and where staff see the suggestion; the privacy text must name the AI provider and the purpose. Write a one-page Article 50 note for the assessor. | Explicit criterion ("where relevant, AI-generated content disclosed"). | Translation labelled; nothing else yet; no Article 50 note. | S | Claude | Open
11 | Critical | Capstone: compliance | "Delete my data" (GDPR): the in-app delete (password check, one transaction, files removed after commit, Neon Auth records) and export exist. Still to do: run one real deletion on the live Neon Auth and watch it work; add the public web page where a person can request deletion (also required by Google Play); make sure the AI check results are removed with the account. | Explicit criterion ("a working delete my data route"). The route is built and tested against the test database; the live Neon Auth deletion has never been exercised. | Built, tested; live Neon Auth deletion untried; no web page. | M | Both | Open
12 | Critical | Capstone: outcome | Phone walk-through on Android with the test accounts (README "Next steps" 2): uploads (portfolio photo, document PDF and photo, chat photo), delete an account (wrong then right password), "Offer services", Open buttons on notices, airplane-mode Retry, the whole Flow 1, and a full Stripe TEST payment (4242 4242 4242 4242; declined 4000 0000 0000 0002; 3-D Secure 4000 0027 6000 3184). Fix what it finds. A new APK is needed first (after Task 10). | The assessor will look at "it runs"; nearly everything in the app has been tested by machines but not walked through by a person on the latest build, and no real Stripe test payment has been made. | Not done. Earlier phone tests found and fixed the keyboard issue; findings 4 and 6 need a production retest. | M | Owner tests, Claude fixes | Open
13 | Critical | Capstone: README | Add a short top section to README.md: ONE paragraph with the goal, the problem it solves and how it works (the current first paragraph is a product summary), plus a Situation-Complication-Resolution summary, the stack, how to run, and a "what is AI-generated" note. Keep the detailed developer part below it. | The brief says: "Create a README.md ... with a paragraph that explains the goal, the problem it solves, and how it works." It is also the first thing assessed. | README is long and detailed but has no clear three-part paragraph and no SCR. | S | Claude | Open
14 | Critical | Capstone: presentation | Prepare the presentation: SCR frame (Situation: households cannot find trustworthy, document-checked helpers and pay safely; Complication: informal markets, no checked documents, no paper trail; Resolution: the marketplace with checked documents, held payment, invoices and chat), the six points (problem, solution and stack, the data, evaluation with the test numbers and reports, challenges such as the deadlock and the RLS guard found in review, what is next), demo accounts and a demo script, screenshots as a fallback. Upload the project to showcase.turingcollege.com before the standup. 10 minutes plus 5 for questions. | Presentation is one of the four evaluation blocks and the showcase upload is required. | Not started. | M | Both | Open
15 | High | Product: Flow 1 | Task 9: full notice text pass for the four new kinds (request-updated, time-proposed, time-to-confirm, quote-confirmed) and the reworded Payment due: in-app, email (en-server, de-server) and German/English review by a native speaker; remove "two new kinds" wording. | Texts are part of the product and the German version is the main one. | Push texts and the mobile map are built; in-app and email texts partly. | S | Claude, owner reads German | Waiting for owner
16 | High | Product: Flow 1 | Task 11: "Quotes sent" (provider) and "My received quotes" (customer) on the account page, with the PDF opened or downloaded and printed from the phone viewer. The server list and PDF link exist (GET /quotes, GET /quotes/[id]/pdf). | The owner asked for it; it is how a quote "can be referred back to". | Server done; screens missing. | M | Claude | Open
17 | High | Product: Flow 1 | Task 12: retire the old proposed-booking path FOR QUOTES and make the time required in the contract (RequestInputSchema); remove the AcceptQuoteScreen route (the old preferredDate field is already removed everywhere: DONE 1 Nov 2026, migration 0027). Keep /quotes/[id]/accept for additional tasks only. The Book button for fixed-price services opens the same request form and POST /bookings plus BookScreen retire (as the approved plan says; instant booking returns with Flow 2). Old proposed rows are still answered until none exist. | Two booking paths side by side invite bugs and double acceptance (the "looping" the owner saw). | Old path still in place on purpose until the app is ready. | M | Claude | Open
18 | High | Product: Flow 1 | Task 13: end of stage: full suites once (web, domain, contract, i18n, mobile), a test report in Reports/, the README update, and a phone test script for Flow 1 including a count of taps before and after (the "fewer clicks" goal). | Owner rule: full suites once at the end of each stage, with a report. | Not done. | M | Claude | Open
19 | High | Product: Flow 1 | Decide the open points of the Flow 1 plan: payment for a quote without a time (default: pay after the time is agreed, built that way); a second PDF of the final agreed booking (optional); the language of the quote PDF (default: German, one language per stored file); street privacy (the street is stored in the request and hidden only in the responses: accept for the MVP or move into a protected place). | These change behaviour and wording; defaults are built. | Defaults built; street privacy raised for the owner. | S | Owner | Open
20 | High | Fixes: phone test | Finding 2: native date and time pickers instead of typed text (deferred by the owner; becomes part of the Task 10 request form). Findings 4 and 6 (a job disappears after its notification is closed; the "Offer services" error): retest on production with the new build. Finding 5: the inbox (top bar icon that turns red, "My requests & bookings" and "Messages" with counts). | Real usability problems from the owner's own phone tests. | Finding 2 deferred; 4 and 6 fixed in code, unconfirmed on production; 5 designed, not built. | M | Both | In progress
21 | High | Hosting: owner actions | Owner dashboard actions (see the Owner actions sheet): Vercel Preview variables and plan, Stripe Preview webhooks, kando-dev and kando-main storage keys, Neon Auth settings, first administrator on production, Resend sending domain and a test email, FCM credentials and a new EAS build. | The production site cannot be demonstrated end to end (admin login, email, push) until these are done. | Open; the first administrator on production is not verified. | M | Owner | Open
22 | High | Demo data | Delete the test accounts that were created on production by a one-off script (garbled umlauts such as "JÃ¼rgen") and create a small clean demo set: one demo customer, two published demo providers with approved documents, a few finished jobs and reviews. Write the demo credentials into the presentation notes, not into the repo. | The assessor needs a believable first screen. Test accounts must not stay on the live site. | Test accounts still on production. | S | Both | Open
23 | High | Quality | Make the repository look finished: lint reports 38 errors in scratch and marketing scripts (move or exclude them), the mobile app has 4 typed-route type errors, CI shows a Node 20 deprecation warning. Aim for green lint, green typecheck, green CI on main. | The assessor will open the repo and the CI tab; a clean state reads as quality. | 38 lint errors and 4 mobile type errors, all older and outside the product code. | S | Claude | Open
24 | High | Legal pages and sign-up | Publish Impressum, Datenschutz, AGB and Ranking in the back office in German and English (drafts in docs/legal-drafts/legal-pages-drafts.md; the owner supplies the company details: legal form, postal address, register entry, VAT rule, jurisdiction, data protection authority, processors). Add the sign-up tick "I am 18 or older and accept the terms and privacy policy". Add "report this profile or photo". | A public live app that takes personal data needs a privacy policy and a consent step; the privacy policy also carries the AI disclosure. | Drafts exist; nothing published; no tick; reporting exists in chat only. | M | Both | Open
25 | High | Compliance | Sign off the data protection impact assessment for the AI document check (draft exists) and sign the processing agreement with the AI provider; record the decision in docs/legal-drafts. | Needed before real personal documents are sent to an AI provider. | Draft only. | S | Owner | Open
26 | High | Evaluation evidence | Collect the evaluation evidence for the presentation: the test counts per package from the final run (web, domain, mobile, contract, i18n), the Excel test reports, the review reports (what reviews found and how it was fixed), the RLS tests, and one measured result for the AI feature (for example how many of 20 sample documents the AI classified like the staff member). | "Evaluation: how do you know it works" is one of the six presentation points; an AI feature needs a measured result. | Reports exist; no AI measurement because there is no AI feature yet. | S | Claude | Open
27 | Medium | Product: bookings | Decide the "tentative" booking state (a provider talks to a customer before accepting): does it hold the time slot, for how long, what does the customer see. Part of the inbox design talk (Finding 5). | Open design question; not needed for the MVP if the chat covers it. | Not designed. | S | Owner | Open
28 | Medium | Product: bookings | Task 14 (optional) and the inbox (finding 5) are ONE list, not two: build "Needs your answer" on Home as the first version of the inbox, so the same information is not built twice. | A "fewer clicks" candidate the owner left optional. | Planned, optional. | M | Claude | Open
29 | Medium | Owner decisions | Decisions before real money (not needed for the capstone): commission percentage (placeholder 12%); cancellation rules (50% after 24 h, 48-hour no-show objection, 7-day stop answer); retention periods; the 25-megapixel photo limit for document scans; how a provider states legal status and VAT id (today everyone is "private" and gets receipts); whether insurance, trade registration and craft qualification become required again; the home texts and store listing; Vercel Pro (needed for commercial use and hourly timers). | Listed in the README "Decisions still to be made"; defaults are built. | Open. | S | Owner | Open
30 | Medium | Stripe | Keep Stripe in TEST mode for the assessment (code refuses live keys); run pnpm payments:smoke on production and Preview; set the Preview webhooks; check the operating rules in the README (do not switch payments off within 24 hours of the last pay link, resend failed events within 3 days). | Capstone case 5 allows Stripe in test mode; the walk-through needs the webhooks to work. | Production webhooks set; Preview webhooks open. | S | Owner | Open
31 | Medium | Robustness | Known gaps worth closing for the MVP if time allows: photo thumbnails (photos load at full size); documents over 4.5 MB cannot be uploaded through Vercel (upload straight to storage); poll Expo push receipts; correction invoices for refunds after payout or chargebacks; invoicing runs inline and slows confirm/cancel/stop (Inngest later); chat contact check is rules only. | Quality and speed on a real phone; none blocks the capstone. | Listed in the README Known gaps. | M | Claude | Open
32 | Medium | Product: Flow 1 | Revisit the stand-in start time: make start_at nullable for awaiting-time (a schema change that touches every reader) or always filter on status. Documented in the README under Known gaps. | Avoids a never-agreed appointment appearing in a future calendar or report. | Documented; later. | M | Claude | Open
33 | Medium | Security | Hosting checks from the assessment: Deployment Protection on previews, fork-PR protection, build-log exposure, a second factor for staff accounts, HSTS subdomain check, Neon Auth cookie flags and login limits, confirm the live app_user role has no BYPASSRLS, GitHub secret scanning and push protection. | Part of the security story and the scan. | Open (owner dashboards). | S | Owner | Open
34 | Medium | Mobile | New EAS build after Task 10 and Task 11 (Android APK, preview profile pointing at https://skillweb.space) and install it on the test phone; iOS only if a paid Apple Developer account exists. | The assessed app must be the current one. | Last build predates Flow 1. | S | Both | Open
35 | Medium | Documentation | Update the README "Where we are", "Next steps" and test numbers after the stage (the README still describes 31 October), and update docs/deployment.md (remove the word "Payload"). | A new session and the assessor read this first. | Out of date after Flow 1. | S | Claude | Open
36 | Low | Flow 2 | Flow 2 (availability rules and instant booking): outline written (docs/superpowers/plans/...flow-2...outline.md). Five owner decisions open. It also needs an owner-connection path to send the provider's quote for instant booking. Recommended: after the capstone. | Larger feature; not needed to pass. | Outline only. | L | Both | Open
37 | Low | Stores | App Store and Google Play: Apple Developer Program and Play Console accounts, listing texts and screenshots in German and English, icon and splash graphics (placeholders today), age rating, data-safety and privacy-label answers, a demo customer and provider for the reviewer, production build and submission (Android internal test first, TestFlight for iOS). | Not required by the capstone (phone or emulator is enough); needed for a public launch. | Not started. | L | Owner | Open
38 | Low | Legal and tax | Lawyer questions (payment licence, 14-day withdrawal, cancellation fees, dispute decisions, reviews, trader documents) and tax adviser questions (VAT on fees, remote job invoices, commission treatment, correction invoices); fill in PLATFORM_ENTITY; switch LIVE_PAYMENTS_ALLOWED only after these. | Needed before real money; the app runs in test mode until then. | Open. | L | Owner | Open
39 | Low | After launch | Post-launch list: deposits, recurring jobs, opening hours and slot picker, per-category cancellation rules, AI help for the chat check, realtime chat with read markers, saved payment method, DAC7 data collection, the Preise page, Inngest for background work. | Deliberately deferred by the owner. | Deferred. | L | Both | Open
40 | Low | Clean-up | Delete the old GitHub repository SkillWeb, the old Vercel project skillweb, the local folder Skilled\skill-web (copy its .env files first if wanted), the old Neon branch main (after kando-dev is detached), the worktree ..\KANDO-phone-test, and the local branches account-address-saved and integration-tmp. | Housekeeping; avoids confusion for the assessor. | Open. | S | Owner | Open
41 | Low | South Africa | Second market later: footer links to German legal pages, language switches assume two languages, one time-zone constant, a missing country fails the postcode check. No work now; avoid new Germany-only assumptions. | Owner decision (memory note): after the German launch. | Parked. | L | Both | Open

## Capstone scorecard
Block | Criterion | Status | Evidence now | Closed by task (No on Tasks sheet)
Outcome quality | Completeness and functionality; runs at a live Vercel URL or on a phone | Partly | Live at https://skillweb.space (production = 31 October release, Stripe TEST mode). The newest work (Flow 1) is on a branch; the app screens are missing; no person has walked the latest build. | Finish Flow 1 (tasks 3, 4), walk-through (12), release sequence (4).
Outcome quality | User interface and interaction quality | Partly | German/English app with tabs, retry states, keyboard fix, placeholder graphics, no inbox, typed date/time fields. | Pickers and inbox (finding 2, 5), graphics, Task 10.
Outcome quality | Clear README.md with a goal / problem / how-it-works paragraph | Partly | Detailed README, but no clear three-part paragraph and no SCR. | Task 13 (README).
Learning application | Course stack: Next.js, Supabase Auth and RLS, Vercel | Met | Next.js 16 and Vercel: yes. Neon Postgres with row-level security and Neon Auth instead of Supabase: approved by the owner (1 November 2026). | Write the evidence note (task 1).
Learning application | CLAUDE.md | Not met | No CLAUDE.md in the project; rules live in the README and private memory. | Task 5.
Learning application | At least one skill, slash command or subagent used | Partly | Used in sessions and now saved in the project .claude folder with a README (branch chore/claude-folder, not merged yet). CLAUDE.md still missing. | Tasks 5, 6.
Learning application | At least one pull request reviewed before merging | Partly | Reviews were done in sessions and written up in Reports/; GitHub records none (0 reviews on 47 PRs). Review records on merged PRs and a GitHub review on the next PR are planned. | Task 7.
Security and compliance | Secrets out of the repo, server side only | Met | All LLM, Stripe and storage calls are server side; the 29 October scan found no secret in history. Preview values and dashboard scoping still open. | Task 9 (re-check, dashboard actions).
Security and compliance | Row-level security on every table holding user data | Met | Every table is classified in rls.ts (private, public-read, staff-only) with a check for unclassified tables; policies, triggers and the app_user role are covered by integration specs. New in review: guard on request columns. | Evidence note (task 1).
Security and compliance | A /security-scan pass | Partly | Last scan 29 October (no critical or high); medium and low items open; code changed a lot since. | Task 8.
Security and compliance | AI-generated content disclosed (Article 50) | Partly | Translate button is labelled "Automatically translated (AI)". No other AI feature yet. | Tasks 2, 10.
Security and compliance | Working "delete my data" route (GDPR) | Partly | In-app delete with password and export are built and tested; the live Neon Auth deletion was never run; no public web page. | Task 11.
Presentation | SCR or SMART framing, clear explanation | Not met | Not started; the facts are ready (README, reports, review reports). | Task 14.
Presentation | Showcase upload and 10 + 5 minute presentation | Not met | Not started. | Task 14.

## Owner decisions
Area | Decision | Recommendation / note | Needed by
Capstone | Is Neon (instead of Supabase) accepted by the course lead? | Ask in writing; the answer decides how much explanation the stack needs. | Before anything else
Capstone | Which AI feature is the capstone feature, and which AI provider? | Recommended: AI check of uploaded documents; provider Mistral through an EU endpoint or an EU-hosted model on OpenRouter, with a processing agreement and no training on the data. | Before the AI build
Capstone | Merge #47 now or hold it until the app screens are ready? | Recommended: hold (see the release warning); merge with the app PR and release together. | Now
Flow 1 | Street privacy: serializer-only hiding (accepted for the MVP) or a protected place for the street until the booking exists? | Raised by the code review of #47; not changed yet. | Before the demo
Flow 1 | Payment for a quote without a time: pay after the time is agreed (default, built). | Confirm. | Task 10
Flow 1 | Second PDF of the final agreed booking; quote PDF language (provider's, default German). | Optional / confirm defaults. | Task 7 follow-up
Product | "Tentative" booking state and the inbox design. | Can wait until after the capstone if the chat covers it. | Optional
Money | Commission percentage (12% placeholder), cancellation rules, retention periods, 25 MP picture limit, provider legal status screen, optional documents, Vercel Pro. | README "Decisions still to be made" 1 to 10. | Before real money
Flow 2 | Five open decisions in the availability and instant booking outline. | Only when Flow 2 is scheduled. | After the capstone

## Owner actions
Where | Action
Vercel | Environment Variables: untick Preview on the live storage keys, RESEND_API_KEY, OPENROUTER_API_KEY, CRON_SECRET; give Preview its own test values; mark secrets Sensitive; check the Stripe key on Preview is a test key.
Vercel | Plan and firewall: confirm four cron jobs are allowed; add rate-limit rules (login, chat, uploads, search) and a body-size rule; check Deployment Protection on previews.
Stripe | Webhook endpoints for the Preview address (with the protection bypass); keep test mode.
Neon | Storage access keys for kando-dev and kando-main; Neon Auth: custom email sending, require email verification, cookie flags, login limits; apply migrations 0024 to 0026 to kando-main BEFORE the Flow 1 release.
Production | First administrator: sign up on the live site, confirm the code, run the SQL from docs/deployment.md against kando-main, walk through the back office once.
Production | Delete the test accounts created by the one-off script; create the demo accounts.
Email | Verify the Resend sending domain and send a test email from production.
Push | Upload the FCM credentials (npx eas-cli credentials), then make a new build; iOS needs a paid Apple Developer account (optional).
GitHub | Turn on secret scanning and push protection; submit a GitHub review (Approve) on a reviewed PR before merging.
Course | Ask the course lead about Neon vs Supabase; register the project on showcase.turingcollege.com; book the standup slot.
Legal | Supply the company details for the legal pages; sign the AI provider processing agreement; sign off the DPIA.

## Reminders
When | What | Who reminds | Status
Before every merge | Run /code-review --comment on the PR, fix the findings, and submit a GitHub review (Approve) in the PR page BEFORE merging. At least for the next release PR (the capstone needs a reviewed PR visible on GitHub). | Claude reminds at each PR | Saved (memory)
AI planning | Discuss the AI quote assistant (drafts the quote text from a request) when the AI feature planning starts. | Claude reminds at AI planning | Saved (memory)
Before the demo | Street privacy question: the street is stored in the request and hidden only in the responses. Accept for the MVP or move it into a protected place? | Claude raises it after Task 10 | Saved (memory)
Later | Stand-in start time for awaiting-time bookings (nullable start_at, or filter on status). Documented in the README Known gaps. | Claude raises it after the capstone | In README
Plan | AI document check: define the human-check rule and the ID-data protection before building. | At AI planning | Open
Now | Reply on the reuse map, direct booking kept until Flow 2, review records on merged PRs, and opening the PR for the .claude folder. | Owner | Waiting for the owner

## Reuse map
Screen or field | Exists today | Reuse / change | Falls away or stays as a known duplicate
Request form (customer) | description, preferredDate (day only, typed), photos | KEEP description and photos; ADD the shared when-and-where fields (reuse TimeProposalForm: date, time, duration, on site, address, note) with native pickers; address prefilled from the saved account address | preferredDate: REMOVED on 1 Nov 2026 (column dropped by migration 0027, contract, server, data export, form, display and texts); nobody uses the app, so nothing is kept for old requests
Shared "when and where" fields | TimeProposalForm: date, time, duration, on site, address, note (used by Book, Accept quote and Counter) | ONE shared component, extracted and given native pickers; used by the request form, the enter-a-time screen and the counter | Nothing duplicated: no second set of fields
Provider answer (quote) | SendQuoteForm: amount, scope, suggested date, time, duration | KEEP and extend: date, time, duration become optional with the switch "date and time confirmed", prefilled from the request; reject exists already (decline) | The "suggestion" label and its text key
Customer quote card | QuoteCard: amount, scope, suggested time, status, validity, Accept button | KEEP; button becomes Confirm (direct call, no time entry); add the quote number, revision, "date and time to be confirmed" and later the PDF link | The navigation to the accept screen
Accept quote screen | AcceptQuoteScreen and /bookings/accept (customer proposes a time after a quote) | - | FALLS AWAY (the customer confirms; the time is in the request and the quote). Server route /quotes/[id]/accept stays for additional tasks
Request page | request-detail: description, preferredDate, quotes, withdraw/decline | KEEP; show time and place; "discuss changes in the chat" instead of editing once a quote exists; Decline offers the chat first; find another provider | preferredDate display (old requests only)
Booking page | booking-detail with pay, cancel, finish, counter sheet (PR 45) | KEEP; add the pending-time block with a confirm button and the awaiting-time text (stand-in time never shown); reuse the OpenChat + enter-time pattern from the counter sheet | Nothing
Counter screen | CounterScreen (counter a proposed booking time) | KEEP for direct bookings; the enter-a-time screen for awaiting-time is the SAME screen with another submit call | No separate form
Direct booking | BookScreen and POST /bookings for fixed-price services | The Book button opens the SAME request form with the service chosen (as the approved plan says: one flow); instant booking returns with Flow 2 | BookScreen and POST /bookings retire in Task 12; old proposed rows are still answered until none exist (known leftover)
Quote lists (Task 11) | New: Quotes sent / My received quotes on the account page | List rows open the EXISTING request page; PDF link on the row | No new detail screen
Inbox / Needs your answer (Task 14, finding 5) | Notices on Home and My bookings | ONE list: build Needs your answer as the first version of the inbox | No separate pop-out or second list
Server fields | requests.start_at, duration_min, on_site, address, note; quotes.start_at, duration_min; bookings.start_at and pending-time columns | All already built and shared through the TimeProposal shape; nothing new to add for the screens | Nothing left to remove: preferredDate is gone; the export now carries startAt, durationMin and onSite

## Change log
When | Commit | What changed | Plan steps / tasks affected
2026-11-02 00:03 | e5717b3 | Workbook is now one file, Reports/MVP Completion Tasks.xlsx, updated in place (owner rule 2 Nov 2026); written now with the current state (steps 1.3 to 1.5)
2026-11-01 23:59 | 9fb1759 | Code review of PR 54: 4 findings fixed, 5 rejected after checking; record posted on the PR
2026-11-01 23:15 | 7022f7e | Steps 1.4 and 1.5 on PR #54: customer confirms a quote directly, Decline offers the chat first, request shows time and place, awaiting-time enter/confirm agreed time; quote lists with PDF link in the account tab | step 1.4 Done, step 1.5 Done
2026-11-01 22:51 | ad81df8 | Step 1.3: provider answer form with pickers, prefill from the request and the Date and time confirmed switch; rule recorded: PRs without code changes are not counted for the workbook | step 1.3 Done
2026-11-01 22:44 | 5a66db1 | AI plan approved by the owner (1 Nov 2026) | step 0.2 Done
2026-11-01 22:41 | 53b1beb | AI plan written (docs/superpowers/plans/2026-11-01-ai-document-check.md) with the owner decisions: human sees only ID problems plus 10% sample, 30-day ID deletion, only verdict and reason stored | step 0.2 Waiting for owner
2026-11-01 22:26 | 3c08c72 | Production migrations 0024-0027 applied by the owner (1 Nov 2026); #49 code confirmed live (quotes route answers 401); live site probes fine
2026-11-01 21:52 | 53b1beb | PRs 48, 49 and 51 merged (51 carries the #50 content, which had been merged into the #49 branch by mistake); step 1.2 on main | step 1.2 Done, merged PR #48, merged PR #49, merged PR #51
2026-11-01 18:29 | 64bafa9 | Code review of PR 50 (/code-review): 7 findings fixed (iPhone picker default and Done button, past time today refused, remote only for remote providers, address prefill once and shared with the time proposal form, 24-hour display); the typed fields of the send-quote form are step 1.3. Review record posted on PR 50.
2026-11-01 18:17 | 2024ae1 | Code review of PR 49 (/code-review): fixed the sweep clock and count, on-demand PDF storing, tracker script robustness; documented the deploy order of migration 0027 (apply after the code); rejected 3 findings (dense versions, trader retention, stricter checks on entering a time). Review record posted on PR 49.
2026-11-01 17:07 | b460758 | Phase 1.2 (Task 10a, Finding 2): one shared set of when-and-where fields (WhenWhereFields, buildProposal) with native date and time pickers, used by the request form and the time proposal form; the request form now sends start, duration, place, address (prefilled from the saved account address) and note, so the app works with the server again. New native dependency @react-native-community/datetimepicker: a new Android build is needed. Owner: review and merge PR 50 (stacked on PR 49), then make the build and test on the phone. | step 1.2 Waiting for owner, task 3 In progress, task 20 In progress
2026-11-01 16:55 | 0f16a5a | CI of PR 48 failed on booking-notifications: the test compared a date without leading zeros (1.1.2027) with the email's 01.01.2027; it failed because today plus 60 days is 1 January. Fixed in the test on both branches (PR 48 and PR 49); my earlier time-of-day explanation was incomplete.
2026-11-01 16:04 | 4373a83 | Phase 0.6 done: review records posted as comments on 12 merged PRs (2, 5, 11, 14, 15, 16, 29, 30, 35, 36, 37, 38) copied from the written reports, and on PRs 47 and 48 (code review of this session). Not posted on 25, 27, 28 and 18 to 20: the reports hold only partial or no code-review lines for them. /code-review 48 was run; findings fixed in PR 48. Still for the owner: submit a GitHub review (Approve) on PR 48 and PR 49 before merging. | step 0.6 Done, task 7 In progress
2026-11-01 16:01 | ec300ca | PR 47 was merged by the owner at its earlier head (2e093d6); the later work (tasks 6b to 9, preferredDate removal, review fixes, tracker) is in the new PR 49 (branch merged with main, conflicts resolved for the branch). PR 48 (CLAUDE.md, .claude folder, RLS note) still open; review records posted on PRs 47 and 48. Production needs migrations 0024 to 0026 (and 0027 with PR 49) - owner to check. | step 1.1 Waiting for owner, task 15 Waiting for owner, merged PR #47
2026-11-01 15:49 | ad03c64 | Review of PR 47 (/code-review): fixed the missing-document sweep and revision numbering, account deletion and data export for quote documents, VAT arithmetic in cents, the checks and the clash check when a time is entered, a stale comment. Rejected or documented: dropped preferredDate column (owner decision), stand-in start time (README), quote expiry cap, no reminder for awaiting-time expiry. Tracker rule changed: the workbook is written after every 2 merged PRs. | step 0.1 In progress
2026-11-01 15:00 | d325b15 | Phase 1.1 (Task 9): notice wording for the one-flow request in German and English (in-app, push, email); the sweep test no longer depends on the time of day (it failed after midday, also without these changes). The owner should read the German texts. Added the /update-mvp-report command. | step 1.1 Done, step 0.1 In progress, task 15 Done
2026-11-01 14:49 | e971d62 | Phase 0.3 and 0.4 on PR #48 (branch chore/claude-folder): CLAUDE.md, the rls-check agent, the /test-report command, project .claude folder with README, RLS and auth evidence note, README section on how the project is built with Claude Code. Waiting for the owner: run /code-review --comment on PR #48, submit a GitHub review, merge. | step 0.3 Waiting for owner, step 0.4 Waiting for owner, task 1 Waiting for owner, task 5 Waiting for owner, task 6 Waiting for owner
2026-11-01 14:45 | ab7813f | Phase 0.5: Tasks 10 to 12 of the Flow 1 plan now carry the confirmed reuse map; the plan keeps the approved one-flow rule (the Book button opens the request form, direct booking retires in Task 12); tracked-update tooling (docs/mvp) added | step 0.5 Done, step 0.1 In progress
2026-11-01 12:00 | 1f9423a | Baseline before the tracked updates: server side of Flow 1 built (tasks 1 to 8 incl. 6a, 6b, 7), the old preferredDate field removed everywhere (migration 0027), the .claude folder pushed on branch chore/claude-folder, owner decisions recorded (Neon approved; AI feature direction). | step 0.1 In progress, step 0.2 In progress, step 0.3 In progress, task 1 In progress