## Summary
KANDO - Registration and one-page provider setup: Test Report
Full suite on branch registration-setup (after fix wave 2 of the independent review), run 27 October 2026: web integration tests on the local Docker database, app and package unit tests. Features only a phone can confirm are marked Not yet done (phone) in Other Checks.
Measure | Value
Automated tests
Passed
Failed
Skipped
Web test files | 35
App test suites | 20
Package tests (contract 9, i18n 14) | 23
Parity rows: Passed / Not yet done (phone) / Open | 18 / 5 / 0

## Test Results
Area | Test file | Test (what it checks) | Part | Outcome
Admin back office API | admin-api.int.spec.ts | lists documents with the pending ones first, with owner email | Web | Passed
Admin back office API | admin-api.int.spec.ts | approving a document makes the service offerable and records the reviewer | Web | Passed
Admin back office API | admin-api.int.spec.ts | rejecting stores the note, and needs one | Web | Passed
Admin back office API | admin-api.int.spec.ts | suspending a user hides the provider from search and the public page; lifting shows it again | Web | Passed
Admin back office API | admin-api.int.spec.ts | suspension emails: none for a customer without a profile, none for a lift of a user who was not suspended | Web | Passed
Admin back office API | admin-api.int.spec.ts | a user suspended before having a profile cannot create one and publish it (409) | Web | Passed
Admin back office API | admin-api.int.spec.ts | lists users with pagination and a text filter on email or name | Web | Passed
Admin back office API | admin-api.int.spec.ts | creates and updates a category per language | Web | Passed
Admin back office API | admin-api.int.spec.ts | creates a page and publishes it | Web | Passed
Admin back office API | admin-api.int.spec.ts | sets a staff role by email; an unknown email is 404 | Web | Passed
Admin back office API | admin-api.int.spec.ts | providers are readable; a Reviewer deletes a photo (object removed, published profile photo unpublishes) | Web | Passed
Admin back office API | admin-api.int.spec.ts | staff see a person's picture on the provider page and the user page, and delete it | Web | Passed
Admin back office API | admin-api.int.spec.ts | GET /me returns the staff user; unknown resources are 404 | Web | Passed
Admin back office API | admin-api.int.spec.ts | a Reviewer cannot decide their own document | Web | Passed
Admin back office API | admin-api.int.spec.ts | an expired suspension is not counted by the suspended filter | Web | Passed
Admin back office API | admin-api.int.spec.ts | GET users/[id] carries names, the private address and the picture; the list shows them too | Web | Passed
Admin back office API | admin-api.int.spec.ts | suspension and published-again emails go to published profiles only; the cron still clears every ended suspension | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLang {"cookie":"en"} -> en | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLang {"cookie":"fr"} -> de | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLang {"cookie":"xx","acceptLanguage":"en"} -> en | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLang {"acceptLanguage":"en-GB,en;q=0.9,de;q=0.8"} -> en | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLang {"acceptLanguage":"fr-FR"} -> de | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLang {} -> de | Web | Passed
Admin lang | admin-lang.int.spec.ts | adminLangCookie lasts a year for the whole site | Web | Passed
Admin lang | admin-lang.int.spec.ts | useAt renders en | Web | Passed
Admin lang | admin-lang.int.spec.ts | useAt renders de | Web | Passed
Admin lang | admin-lang.int.spec.ts | admin layout follows the cookie, then Accept-Language, then German | Web | Passed
Staff roles | admin-roles.int.spec.ts | a Reviewer cannot do Administrator actions, and nothing changes | Web | Passed
Staff roles | admin-roles.int.spec.ts | a Reviewer cannot change or delete an existing category or page | Web | Passed
Staff roles | admin-roles.int.spec.ts | a Reviewer can read users and documents | Web | Passed
Staff roles | admin-roles.int.spec.ts | a customer with no staff role gets 403 on every admin route; no session gets 401 | Web | Passed
Staff roles | admin-roles.int.spec.ts | the last Administrator cannot be demoted | Web | Passed
Staff roles | admin-roles.int.spec.ts | every route file under app/api/admin exports handlers built with adminRequest | Web | Passed
Security rule check | app-endpoints-wrapped.int.spec.ts | the owner-connection check catches a bypass (negative fixture) | Web | Passed
Security rule check | app-endpoints-wrapped.int.spec.ts | every route file under app/app-api exports handlers built with appRequest | Web | Passed
App request wrapper | app-request.int.spec.ts | first contact creates the users row | Web | Passed
App request wrapper | app-request.int.spec.ts | a forged cookie is 401 and touches nothing | Web | Passed
App request wrapper | app-request.int.spec.ts | required auth without a cookie is 401 | Web | Passed
App request wrapper | app-request.int.spec.ts | optional auth without a cookie runs with no user | Web | Passed
App request wrapper | app-request.int.spec.ts | an unconfirmed email: 403 where auth is required, signed out where optional; never a users row | Web | Passed
App request wrapper | app-request.int.spec.ts | a handler error rolls back and returns 500 | Web | Passed
App request wrapper | app-request.int.spec.ts | a body over maxBodyBytes is 413 before the handler runs | Web | Passed
App request wrapper | app-request.int.spec.ts | user A cannot read user B through the wrapper | Web | Passed
App request wrapper | app-request.int.spec.ts | app_user cannot write staff columns of its own row | Web | Passed
App request wrapper | app-request.int.spec.ts | first contact with a changed email updates the row | Web | Passed
App request wrapper | app-request.int.spec.ts | a second id with the same email gets 409 and no row is written | Web | Passed
App request wrapper | app-request.int.spec.ts | a thrown 400 Response is returned unchanged | Web | Passed
Sign-up and session | auth-cookie-flow.int.spec.ts | auth cookie flow signs up by REST, captures the cookie; /app-api/v1/me knows the session but refuses it until the email is confirmed | Web | Passed
Categories | categories.int.spec.ts | ordered by sort, "other services" always last, names in the requested language, anonymous allowed | Web | Passed
Categories | categories.int.spec.ts | an unknown language is 400 | Web | Passed
Concurrency | concurrency.int.spec.ts | 12 concurrent searches and 12 concurrent public pages all complete | Web | Passed
Cron suspensions | cron-suspensions.int.spec.ts | 401 without the right secret, and when CRON_SECRET is unset | Web | Passed
Cron suspensions | cron-suspensions.int.spec.ts | ends a past suspension once: both columns cleared, one email; a future one is left alone | Web | Passed
Database migrations | db-migrations.int.spec.ts | migrates an empty database and classifies every table | Web | Passed
Database migrations | db-migrations.int.spec.ts | 0008: person fields on users, suspensions by date, drafts allowed, notifications; applyRls succeeds | Web | Passed
Database migrations | db-migrations.int.spec.ts | photos: a profile photo has no provider, a portfolio photo has one, one profile photo per person | Web | Passed
Database migrations | db-migrations.int.spec.ts | 0008 on a database with data: a suspended provider stays hidden, a published one without names or picture goes back to draft | Web | Passed
Emails | email.int.spec.ts | approval: one email in the user language with the document name and the deep link | Web | Passed
Emails | email.int.spec.ts | rejection in German includes the note verbatim, escaped in the HTML | Web | Passed
Emails | email.int.spec.ts | without a key it only logs and records, and never throws | Web | Passed
Emails | email.int.spec.ts | outside tests without a key: one log line without recipient or body, and nothing kept in memory | Web | Passed
Emails | email.int.spec.ts | with a key it calls Resend with the full message; an { error } and a throw are logged, not thrown | Web | Passed
Emails | email.int.spec.ts | an unexpected stored language falls back to German | Web | Passed
Uploads and document review | files-review.int.spec.ts | afterCommit: a handler that deletes a photo and then throws rolls back, the object stays | Web | Passed
Uploads and document review | files-review.int.spec.ts | afterCommit: the object is deleted only after the commit | Web | Passed
Uploads and document review | files-review.int.spec.ts | private_files and documents are isolated (RLS) | Web | Passed
Uploads and document review | files-review.int.spec.ts | at most 10 unsubmitted uploads per user (409) | Web | Passed
Uploads and document review | files-review.int.spec.ts | a decompression bomb and a header followed by garbage are 400; a later upload is accepted | Web | Passed
Uploads and document review | files-review.int.spec.ts | EXIF is stripped from the stored JPEG | Web | Passed
Uploads and document review | files-review.int.spec.ts | alt over 200 characters is 400 | Web | Passed
Uploads and document review | files-review.int.spec.ts | an unauthenticated upload is refused before the body is read | Web | Passed
Uploads and document review | files-review.int.spec.ts | the body is read before the first-contact user row and the transaction exist | Web | Passed
Uploads and document review | files-review.int.spec.ts | photos of a published provider are public, and unreadable once suspended | Web | Passed
Uploads and document review | files-review.int.spec.ts | replacing the profile photo of a published profile works | Web | Passed
Uploads and document review | files-review.int.spec.ts | deleting the profile photo while publishing never leaves a published profile without a photo | Web | Passed
Uploads and document review | files-review.int.spec.ts | two simultaneous submits for one requirement give one 201 and one 409 | Web | Passed
Uploads and document review | files-review.int.spec.ts | the database refuses a second pending check for a requirement | Web | Passed
Uploads and document review | files-review.int.spec.ts | approval (staff SQL) makes a service with required documents offerable | Web | Passed
Uploads and document review | files-review.int.spec.ts | the signed link carries X-Amz-Expires=300 and the public URL needs AWS_ENDPOINT | Web | Passed
Uploads | files.int.spec.ts | a profile photo is re-encoded to JPEG at most 1600 px and returned in contract shape | Web | Passed
Uploads | files.int.spec.ts | a new profile photo replaces the old one and deletes its object | Web | Passed
Uploads | files.int.spec.ts | portfolio is limited to 12 (409), a non-image is 400, a missing kind is 400 | Web | Passed
Uploads | files.int.spec.ts | a portfolio photo needs a profile first (409); anonymous is 401; an oversize body is 413 | Web | Passed
Uploads | files.int.spec.ts | deleting a photo: another user gets 404, the owner 204 and the object and row are gone | Web | Passed
Uploads | files.int.spec.ts | the profile photo of a published profile cannot be deleted (409) | Web | Passed
Uploads | files.int.spec.ts | suspended_until is domain-only and photos are isolated | Web | Passed
Uploads | files.int.spec.ts | files: a PDF goes to the private bucket, a non-PDF is 400, another user gets 404, the owner a signed link | Web | Passed
Uploads | files.int.spec.ts | documents also take JPEG, PNG and WEBP photos: re-encoded without metadata, at most 2400 px, stored with their type | Web | Passed
Uploads | files.int.spec.ts | a GIF and a text file renamed to .pdf are refused as documents | Web | Passed
Uploads | files.int.spec.ts | staff open an image document through the same signed link; it is served as an image | Web | Passed
Uploads | files.int.spec.ts | a failed file insert removes the uploaded object | Web | Passed
Uploads | files.int.spec.ts | verifications: one pending check per requirement (409 removes the second file), bad input is 400 | Web | Passed
Uploads | files.int.spec.ts | the profile photo is private to its owner: another user cannot see it and gets 404 on delete; listPhotos puts it first | Web | Passed
Website home page | home-page.int.spec.ts | home page is German by default: headline, categories, store badges without links, no forbidden words | Web | Passed
Website home page | home-page.int.spec.ts | home page switches to English with ?lang=en and falls back to German for unknown values | Web | Passed
Website home page | home-page.int.spec.ts | home page has per-language metadata with canonical and hreflang for every language | Web | Passed
Website home page | home-page.int.spec.ts | site layout metadataBase makes canonical and hreflang absolute on the site url | Web | Passed
Website home page | home-page.int.spec.ts | site layout html lang follows the request language; unknown falls back to de | Web | Passed
Website home page | home-page.int.spec.ts | site layout footer links the four legal pages with catalogue labels in both languages | Web | Passed
Notifications | notifications.int.spec.ts | live and nothing else pending: "profile is live" email with the link, and one notification | Web | Passed
Notifications | notifications.int.spec.ts | the link of a German provider has no lang parameter | Web | Passed
Notifications | notifications.int.spec.ts | live but another document is still missing: says the category service is visible, no notification | Web | Passed
Notifications | notifications.int.spec.ts | the approved requirement is not enough for any service: plain approval, no notification | Web | Passed
Notifications | notifications.int.spec.ts | draft profile: offline text, no notification | Web | Passed
Notifications | notifications.int.spec.ts | suspended profile: suspended text with the date, no notification | Web | Passed
Notifications | notifications.int.spec.ts | a requirement that was already approved: plain approval, no notification | Web | Passed
Notifications | notifications.int.spec.ts | rejection is unchanged | Web | Passed
Notifications | notifications.int.spec.ts | GET /me lists the notification; PATCH dismissed hides it; another user gets 404 | Web | Passed
Database connection | owner-connection.int.spec.ts | inside a request transaction the owner connection `db` is a different connection (not app_user) | Web | Passed
Database connection | owner-connection.int.spec.ts | two interleaved requests keep their own user id and role | Web | Passed
Legal and info pages | pages.int.spec.ts | pages tables every table is classified (pages and page_texts are public reference tables) | Web | Passed
Legal and info pages | pages.int.spec.ts | pages tables anonymous app requests read pages but cannot write them | Web | Passed
Legal and info pages | pages.int.spec.ts | getPage returns the text in the language, falls back to de, hides drafts and unknown slugs | Web | Passed
Legal and info pages | pages.int.spec.ts | getPage publishedPages lists published pages only | Web | Passed
Legal and info pages | pages.int.spec.ts | legal page by slug renders the Markdown body in both languages with the de fallback | Web | Passed
Legal and info pages | pages.int.spec.ts | legal page by slug 404 for unknown and unpublished slugs | Web | Passed
Legal and info pages | pages.int.spec.ts | legal page by slug metadata: title, canonical and hreflang for every language | Web | Passed
Legal and info pages | pages.int.spec.ts | legal page by slug escapes HTML in a body and drops unsafe links | Web | Passed
Legal and info pages | pages.int.spec.ts | renderMarkdown escapes raw html and keeps Markdown | Web | Passed
Legal and info pages | pages.int.spec.ts | renderMarkdown external links get rel="nofollow ugc"; protocol-relative and backslash paths are dropped | Web | Passed
Postcodes | postcodes.int.spec.ts | imports the German file and looks up 01053 Dresden | Web | Passed
Postcodes | postcodes.int.spec.ts | rejects a four-digit German code and an unknown one | Web | Passed
Postcodes | postcodes.int.spec.ts | Berlin to Munich is about 504 km | Web | Passed
Website provider page | provider-page.int.spec.ts | public provider page German default: public name heading, category, price "ab 80,00 â‚¬", on request, place | Web | Passed
Website provider page | provider-page.int.spec.ts | public provider page English with ?lang=en: "from â‚¬80.00" | Web | Passed
Website provider page | provider-page.int.spec.ts | public provider page escapes user content | Web | Passed
Website provider page | provider-page.int.spec.ts | public provider page 404 for a hidden provider (draft) and an unknown slug | Web | Passed
Website provider page | provider-page.int.spec.ts | public provider page metadata: title, description, canonical and hreflang for every language | Web | Passed
Website provider page | provider-page.int.spec.ts | translate link is shown only when the texts are not in the page language | Web | Passed
Website provider page | provider-page.int.spec.ts | translate link ?translate=1 shows the translation with the AI label, noindex, canonical unchanged | Web | Passed
Website provider page | provider-page.int.spec.ts | translate link ?translate=1 without a key shows the original texts and the unavailable copy | Web | Passed
Website provider page | provider-page.int.spec.ts | translate link translate=1 on texts already in the viewer language: original, no label, no model call | Web | Passed
Provider profile | provider-profile.int.spec.ts | GET is null when there is no profile | Web | Passed
Provider profile | provider-profile.int.spec.ts | PUT creates (201) and a later PUT edits (200); responses fit the contract | Web | Passed
Provider profile | provider-profile.int.spec.ts | an unknown postcode is 400 and changes nothing | Web | Passed
Provider profile | provider-profile.int.spec.ts | a partial first save never fails on business rules | Web | Passed
Provider profile | provider-profile.int.spec.ts | status, slug and suspended in the body are ignored | Web | Passed
Provider profile | provider-profile.int.spec.ts | one user's profile is not visible to another | Web | Passed
Provider profile | provider-profile.int.spec.ts | an invalid body is 400 with the contract error | Web | Passed
Provider profile | provider-profile.int.spec.ts | an unconfirmed email gets 403 EMAIL_NOT_VERIFIED from PUT provider-profile and GET /me, and no users row | Web | Passed
Provider profile | provider-profile.int.spec.ts | PATCH /me checks its body with the contract: 400 Invalid input names the field; a valid patch saves | Web | Passed
Provider profile | provider-profile.int.spec.ts | a user without an address still gets a draft (the provider row default country applies) | Web | Passed
Provider profile | provider-profile.int.spec.ts | POST creates a draft with the postcode prefilled; again returns the same id; GET /me is fine | Web | Passed
Provider profile | provider-profile.int.spec.ts | missing: the empty draft lists the person-independent items, business adds two, saves shrink it, PUT carries it | Web | Passed
Provider profile | provider-profile.int.spec.ts | publish of an incomplete draft is 409 with the list; complete publishes with public name Lena F. | Web | Passed
Provider profile | provider-profile.int.spec.ts | a draft with every nullable field null is invisible in search and the sitemap | Web | Passed
Provider profile | provider-profile.int.spec.ts | a draft created during a suspension cannot be published | Web | Passed
Provider profile | provider-profile.int.spec.ts | the draft prefills the postcode only when it is a known one | Web | Passed
Provider profile | provider-profile.int.spec.ts | a live profile cannot be emptied by a save: 409 with the missing list, nothing changed | Web | Passed
Provider profile | provider-profile.int.spec.ts | a provider whose names are missing cannot publish: missing lists name | Web | Passed
Provider profile | provider-profile.int.spec.ts | the draft's postcode lookup uses the owner's stored country | Web | Passed
Public provider data | provider-public.int.spec.ts | a published provider page: contract shape, place, photo urls, only offerable services | Web | Passed
Public provider data | provider-public.int.spec.ts | 404 when not visible: unknown, draft, or no offerable service | Web | Passed
Public provider data | provider-public.int.spec.ts | a draft page is a 404 for its own owner too | Web | Passed
Public provider data | provider-public.int.spec.ts | unknown language is 400 | Web | Passed
Public provider data | provider-public.int.spec.ts | anonymous: the page carries the owner's profile photo and the public name, no display name | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | returns translated texts in the page shape | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | a draft or suspended provider -> 404, no call | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | unknown lang -> 400 | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | service failure -> 503 and nothing stored | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | a logged-in caller is counted under the user id | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | the provider endpoint reports translatable per viewer language | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | accepts no text from the client | Web | Passed
Translate endpoint | provider-translation.int.spec.ts | fails closed without a usable secret: 503, no counter row, no model call | Web | Passed
Site and admin routing | proxy.int.spec.ts | /admin and below go through the auth middleware | Web | Passed
Site and admin routing | proxy.int.spec.ts | /administrator or a page slug starting with admin is a site path with x-lang | Web | Passed
Public name | public-name.int.spec.ts | publicNameFor: business name, else first name and surname initial | Web | Passed
Public name | public-name.int.spec.ts | slugify transliterates umlauts and strips the rest | Web | Passed
Public name | public-name.int.spec.ts | public name and slug are unique and stable | Web | Passed
Public name | public-name.int.spec.ts | an individual without names cannot publish; with names the public name follows | Web | Passed
Public name | public-name.int.spec.ts | first contact does not copy the session name: the person sets their own names | Web | Passed
Public name | public-name.int.spec.ts | a rename of the person changes the public name of their provider profile | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | the first-time flow: refused until photo and service exist, then published, then unpublished | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | a postcode-less profile is refused until a postcode is saved | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | a suspended profile cannot publish (409) | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: published and not suspended is public, drafts and suspended are not | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: another user cannot change or add to a provider; domain-only columns are closed | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: set_provider_* touch only the caller's own profile | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | RLS: documents are private and the verdict is staff-only | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | offerableServiceIds: services whose required documents are all approved | Web | Passed
Publish and unpublish | publish-flow.int.spec.ts | a user suspension that has ended no longer blocks publishing; a running one does | Web | Passed
Staff check | require-staff.int.spec.ts | an active admin passes | Web | Passed
Staff check | require-staff.int.spec.ts | a suspended admin gets 403 | Web | Passed
Staff check | require-staff.int.spec.ts | an expired suspension no longer blocks | Web | Passed
Row-level security | rls-providers.int.spec.ts | another user cannot update or delete a service or a reference (rowCount 0, rows unchanged) | Web | Passed
Row-level security | rls-providers.int.spec.ts | another user cannot insert a service or a reference for my provider | Web | Passed
Row-level security | rls-providers.int.spec.ts | the owner cannot move a service to another provider | Web | Passed
Row-level security | rls-providers.int.spec.ts | offerableServiceIds and missingRequirements are identical through tx and the owner db | Web | Passed
Row-level security | rls-providers.int.spec.ts | a stranger asking about a draft provider gets empty answers; the owner still gets the full ones | Web | Passed
Row-level security | rls-providers.int.spec.ts | a service with a category alone (no price type yet) is never offerable, not even to its owner | Web | Passed
Row-level security | rls-providers.int.spec.ts | slugify strips accents | Web | Passed
Row-level security | rls.int.spec.ts | app_user cannot read a private table row of another user | Web | Passed
Row-level security | rls.int.spec.ts | public reference tables are readable by app_user and not writable | Web | Passed
Row-level security | rls.int.spec.ts | a person's picture is private until the owner's provider is published and not suspended | Web | Passed
Row-level security | rls.int.spec.ts | notifications: the owner reads and marks own rows; another user sees none, cannot insert or change kind | Web | Passed
Search | search.int.spec.ts | radius edge and remote providers | Web | Passed
Search | search.int.spec.ts | a remote provider more than 200 km away is found, without a distance | Web | Passed
Search | search.int.spec.ts | a draft is invisible to its owner too | Web | Passed
Search | search.int.spec.ts | distance is whole km, at least 1, hidden for remote providers outside the radius | Web | Passed
Search | search.int.spec.ts | a draft, a suspended or a provider without an offerable service never appears | Web | Passed
Search | search.int.spec.ts | category filter and q (public name and skills, case-insensitive) | Web | Passed
Search | search.int.spec.ts | bad input is 400: unknown postcode, bad format, unknown country, unknown language, bad page | Web | Passed
Search | search.int.spec.ts | paging: 20 per page and hasMore | Web | Passed
Search | search.int.spec.ts | anonymous: the card carries the owner's profile photo and the public name, no display name | Web | Passed
Search | search.int.spec.ts | a provider whose only service has no price type is neither found nor has a public page | Web | Passed
Search | search.int.spec.ts | a fixed service without a price is not found in its category | Web | Passed
Seeds | seeds.int.spec.ts | categories seed is idempotent: 14 categories, both names, babysitting needs a police certificate | Web | Passed
Seeds | seeds.int.spec.ts | postcode import upserts: a second run leaves the same count | Web | Passed
Seeds | seeds.int.spec.ts | the dev guard needs the dev branch AND the dev database host | Web | Passed
Seeds | seeds.int.spec.ts | loadSeedData reads the git-ignored list or the committed example, and rejects a broken file | Web | Passed
Seeds | seeds.int.spec.ts | seedTestUsers itself refuses outside dev, before touching anything | Web | Passed
Seeds | seeds.int.spec.ts | builds the test users through the domain: published providers with photo, services, public names, verified; a rerun adds nothing | Web | Passed
Seeds | seeds.int.spec.ts | a run that crashed after the services (no photo, not published) resumes without adding the services twice | Web | Passed
Seeds | seeds.int.spec.ts | placeholder photos: gives a published profile without a photo one; elsewhere needs the typed yes | Web | Passed
Seeds | seeds.int.spec.ts | neonAuth retries a 429, then succeeds | Web | Passed
Seeds | seeds.int.spec.ts | neonAuth signs in when the email already exists | Web | Passed
Seeds | seeds.int.spec.ts | neonAuth surfaces any other sign-up failure without falling back to sign-in | Web | Passed
Services and references | services-references.int.spec.ts | a service needs a profile first (409) | Web | Passed
Services and references | services-references.int.spec.ts | create, list and patch a service; shapes fit the contract | Web | Passed
Services and references | services-references.int.spec.ts | on-request has no price, even when one is sent | Web | Passed
Services and references | services-references.int.spec.ts | bad service input: no price, three decimals, unknown category are 400 | Web | Passed
Services and references | services-references.int.spec.ts | a service in a category with required documents waits for approval | Web | Passed
Services and references | services-references.int.spec.ts | user A cannot edit or delete user B's service | Web | Passed
Services and references | services-references.int.spec.ts | references are capped at 2 (409), can be patched and deleted | Web | Passed
Services and references | services-references.int.spec.ts | a service with a category alone is saved, not offerable, and a patch accepts the partial shape | Web | Passed
Services and references | services-references.int.spec.ts | the price type and the price save in either order, each as its own one-field save | Web | Passed
Services and references | services-references.int.spec.ts | a fixed service without a price is not offerable, with a price it is; on-request clears the price | Web | Passed
Services and references | services-references.int.spec.ts | the app sends a category alone, then one field per save: currency defaults to EUR, title to the category name | Web | Passed
Services and references | services-references.int.spec.ts | add and update answer with waitingFor and visibleInSearch, like the list | Web | Passed
Sitemaps | sitemaps.int.spec.ts | providers sitemap lists only visible providers | Web | Passed
Sitemaps | sitemaps.int.spec.ts | pages sitemap lists the home page and published pages only | Web | Passed
Sitemaps | sitemaps.int.spec.ts | robots.txt allows the site, keeps the admin out and points at both sitemaps | Web | Passed
Smoke test | smoke.int.spec.ts | connects to the test database and sees PostGIS | Web | Passed
Test database guard | test-guard.int.spec.ts | the test guard refuses a non-local or non-test URL | Web | Passed
Translate | translate.int.spec.ts | translate stores translations and serves the second request from the store without a call | Web | Passed
Translate | translate.int.spec.ts | translate an edited text is re-translated, the rest comes from the store | Web | Passed
Translate | translate.int.spec.ts | translate texts already in the target language are returned unchanged without a call | Web | Passed
Translate | translate.int.spec.ts | translate a malformed or incomplete model answer stores nothing and throws TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | translate a non-2xx answer throws TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | translate line breaks survive | Web | Passed
Translate | translate.int.spec.ts | translate no key -> TranslationUnavailable without a call | Web | Passed
Translate | translate.int.spec.ts | translate the 31st AI call within an hour for one client key -> TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | translate the limit boundary: the 30th call passes, the 31st is refused | Web | Passed
Translate | translate.int.spec.ts | translate a timeout -> TranslationUnavailable | Web | Passed
Translate | translate.int.spec.ts | translate concurrent translations of the same page store one row per text | Web | Passed
Translate | translate.int.spec.ts | translate writes through the request transaction and commits with it | Web | Passed
Translate | translate.int.spec.ts | translate the default timeout is 12 seconds | Web | Passed
Translate | translate.int.spec.ts | translate French and Afrikaans texts are flagged and sent to the model, in either viewer language | Web | Passed
Translate | translate.int.spec.ts | translate a page the detector cannot classify is translated when long enough, left alone when short | Web | Passed
Translate | translate.int.spec.ts | translate a German profile of short skills and titles needs no translation for de but does for en | Web | Passed
Translate | translate.int.spec.ts | translate a Markdown-fenced answer parses; the request carries max_tokens | Web | Passed
Translate | translate.int.spec.ts | translate an empty string from the model stores nothing | Web | Passed
Translate | translate.int.spec.ts | translate counter rows older than 24 hours are deleted; recent ones stay | Web | Passed
Translate | translate.int.spec.ts | translate anonymous client keys are salted hashes, never the raw IP | Web | Passed
Translate | translate.int.spec.ts | translate textsOf picks the translatable fields of a profile | Web | Passed
Translate | translate.int.spec.ts | translate needsTranslation is false for a page entirely in the viewer language and true for a mixed page | Web | Passed
Translate | translate.int.spec.ts | translation tables are insert-only for app_user anonymous callers can insert and read, never update or delete | Web | Passed
Phone app | profile-form.test.ts | server errors land on the right field | App | Passed
Phone app | profile-form.test.ts | withItem adds a trimmed new skill or strength once and ignores blanks | App | Passed
Phone app | profile-form.test.ts | the form-level error shows unless every server error has an inline slot | App | Passed
Phone app | profile-form.test.ts | service and reference validation | App | Passed
Phone app | profile-form.test.ts | every missing item the publish route can return has de and en text | App | Passed
Phone app | profile-form.test.ts | the service body names the category by id and the currency, as the server expects | App | Passed
Phone app | profile-form.test.ts | a 400 "Invalid input" marks each named field | App | Passed
Phone app | profile-form.test.ts | live means published and not suspended now (the server rule of listServices) | App | Passed
Share profile | share-profile.test.ts | the provider page url carries the language only when it is not the default | App | Passed
Share profile | share-profile.test.ts | shareProfile passes the url and the text in the given language | App | Passed
Address fields | address-fields.test.ts | toAddress: empty is null (clears), complete is DE, partial is undefined | App | Passed
Phone app | index.test.ts | texts come from the shared catalogue, in the chosen language, with placeholders filled | App | Passed
Phone app | index.test.ts | the translate button texts exist in both languages | App | Passed
Phone app | index.test.ts | errorText maps the auth server codes to catalogue messages | App | Passed
Phone app | index.test.ts | errorText maps the app API strings | App | Passed
Phone app | index.test.ts | docText maps known document codes and passes unknown ones through | App | Passed
Phone app | format.test.ts | prices follow the website rules in German and English | App | Passed
Phone app | format.test.ts | distance shows km, remote or nothing | App | Passed
Phone app | format.test.ts | search path leaves out empty filters and trims text | App | Passed
Phone app | format.test.ts | photoSrc loads only absolute http(s) URLs, never a server-relative /api path | App | Passed
Phone app | auth.test.ts | signUp posts email, password and name and stores the session cookie | App | Passed
Phone app | auth.test.ts | signIn posts email and password and returns the user | App | Passed
Phone app | auth.test.ts | a refused sign-in throws the server code, which maps to a catalogue message | App | Passed
Phone app | auth.test.ts | signOut forgets the session at once and tells the server with the old cookie | App | Passed
Phone app | auth.test.ts | signOut offline still signs out | App | Passed
Phone app | auth.test.ts | session reads get-session with the cookie; no cookie means null without a request | App | Passed
Phone app | auth.test.ts | session throws on a network error (the app offers a retry, not the login) | App | Passed
Phone app | auth.test.ts | sendVerificationCode asks for an email-verification code | App | Passed
Phone app | auth.test.ts | verifyEmail sends the code as otp, stores the new session and returns the user | App | Passed
Phone app | auth.test.ts | requestPasswordReset asks for a reset code | App | Passed
Phone app | auth.test.ts | resetPassword sends email, code and the new password | App | Passed
Phone app | auth.test.ts | a wrong code throws INVALID_OTP, shown as the code message | App | Passed
Phone app | auth.test.ts | signUp and signIn start without an old stored session | App | Passed
Phone app | my-profile.test.ts | a failed check after the upload deletes the uploaded file and reports the original error | App | Passed
Phone app | my-profile.test.ts | a successful submit deletes nothing | App | Passed
Phone app | my-profile.test.ts | a failing clean-up does not hide the original error | App | Passed
Phone app | pick.test.ts | preparePhoto keeps the long side at 1600 px | App | Passed
Phone app | pick.test.ts | tooLarge is true above 4_434_464 bytes | App | Passed
Phone app | pick.test.ts | pickPhoto cancelled is null | App | Passed
Phone app | pick.test.ts | pickPhoto a refused permission is denied, not cancelled | App | Passed
Phone app | pick.test.ts | pickDocument offers PDFs and the image types the server accepts, from any file source | App | Passed
Phone app | pick.test.ts | pickDocument cancelled is null | App | Passed
Pending signup | pending-signup.test.ts | the pending record round-trips and clears | App | Passed
Phone app | translation.test.ts | applyTexts swaps only the translatable fields and keeps names, prices and photos | App | Passed
Phone app | translation.test.ts | applyTexts matches services and references by id and leaves unknown ones untouched | App | Passed
Phone app | translation.test.ts | applyTexts keeps line breaks | App | Passed
Phone app | client.test.ts | sends the stored cookie and stores a new set-cookie | App | Passed
Phone app | client.test.ts | a single joined set-cookie header (no getSetCookie) is split into its cookies | App | Passed
Phone app | client.test.ts | clears the session on 401 | App | Passed
Phone app | client.test.ts | a 401 without a stored session does not call onUnauthorized | App | Passed
Phone app | client.test.ts | every request names the app origin and leaves the platform cookie store out | App | Passed
Phone app | client.test.ts | a 409 with error and missing throws ApiError with code and missing | App | Passed
Phone app | client.test.ts | a 400 "Invalid input" lists the fields named by its issues | App | Passed
Phone app | client.test.ts | a network failure throws ApiError(0, network) | App | Passed
Phone app | client.test.ts | a server that never answers fails as network after the time limit | App | Passed
Phone app | client.test.ts | saves have no time limit: a slow save that succeeds is not reported as a failure | App | Passed
Phone app | client.test.ts | updateMe PATCHes the account name | App | Passed
Phone app | client.test.ts | upload sends multipart with the cookie and no time limit | App | Passed
Phone app | client.test.ts | upload sends the file bytes with its name and type, not a bare { uri } object | App | Passed
Phone app | client.test.ts | a file the phone cannot open is "File unreadable", not a network error, and nothing is sent | App | Passed
Phone app | client.test.ts | upload maps a 413 to ApiError "File too large" | App | Passed
Phone app | client.test.ts | upload maps a network failure to ApiError network and does not retry | App | Passed
Phone app | client.test.ts | a store that cannot be read (Keystore failure) sends the request without a cookie | App | Passed
Phone app | client.test.ts | a cookie that cannot be saved does not fail a request the server already carried out | App | Passed
Phone app | client.test.ts | a malformed Set-Cookie line without "=" is skipped | App | Passed
Phone app | client.test.ts | updateMe sends the one-field name as first and last name, split at the last space | App | Passed
Phone app | use-session.test.ts | loading -> signed in -> signed out | App | Passed
Phone app | use-session.test.ts | an unverified email never counts as signed in: sign-in sends a code and asks for it | App | Passed
Phone app | use-session.test.ts | a server that refuses unverified sign-ins (EMAIL_NOT_VERIFIED) also leads to the code screen | App | Passed
Phone app | use-session.test.ts | sign-up creates the account and sends the code; the right code signs in and saves the account name | App | Passed
Phone app | use-session.test.ts | a wrong code throws and keeps signed out | App | Passed
Phone app | use-session.test.ts | a failed login rejects and keeps signed out; a server error on load means signed out | App | Passed
Phone app | use-session.test.ts | a network error on load sets offline (not signed out); retry recovers | App | Passed
Phone app | use-session.test.ts | onUnauthorized from the API client signs the user out | App | Passed
Phone app | use-session.test.ts | switching the language also saves it for emails, but only while signed in | App | Passed
Phone app | use-session.test.ts | verify finishes the sign-up: names and address, then the picture, then the record is cleared; returns the tick | App | Passed
Phone app | use-session.test.ts | a failed upload keeps the record; loadSession retries it once and clears it | App | Passed
Phone app | use-session.test.ts | loadSession without a record or while signed out does not finish a sign-up | App | Passed
Phone app | use-session.test.ts | a record for another email is dropped and applies nothing | App | Passed
Phone app | use-session.test.ts | a failed PATCH keeps the full record | App | Passed
Phone app | use-session.test.ts | after the PATCH succeeded, a failed upload keeps only email, tick and picture; the retry does not PATCH again | App | Passed
Phone app | use-session.test.ts | a picture whose cached file is gone is dropped and the record cleared | App | Passed
Phone app | use-session.test.ts | sign-up keeps the record for the code step; a failed sign-up leaves none | App | Passed
Phone app | use-session.test.ts | finishing a sign-up reloads /me so the home nudge sees the new picture; nothing to finish, nothing to reload | App | Passed
Picture nudge | picture-nudge.test.ts | the dismissed-nudge key is per user, so a second account on the device still sees it | App | Passed
Use field save | use-field-save.test.ts | two quick changes become one request with the last value | App | Passed
Use field save | use-field-save.test.ts | flush saves immediately and nothing is sent twice | App | Passed
Use field save | use-field-save.test.ts | a rejected save marks error and retry resends the same value | App | Passed
Use field save | use-field-save.test.ts | a change typed while a save is in flight is sent after it, in order | App | Passed
Use field save | use-field-save.test.ts | dispose sends a pending change so nothing typed is lost | App | Passed
Phone app | match.test.ts | matches ignores case and accents, and an empty query matches everything | App | Passed
Phone app | auth-layout.test.ts | logged-out landing route is login | App | Passed
Phone app | auth-layout.test.ts | no test files inside src/app (each file there becomes a screen) | App | Passed
Stale guard | stale-guard.test.ts | a response older than one already applied is ignored | App | Passed
Stale guard | stale-guard.test.ts | answers arriving in order are all applied | App | Passed
Serial create | serial-create.test.ts | choosing twice before the create returns creates once, then updates | App | Passed
Serial create | serial-create.test.ts | an existing id is only updated | App | Passed
Phone app | documents.test.ts | no rows when no service needs a document | App | Passed
Phone app | documents.test.ts | a babysitting service with nothing uploaded â†’ police-certificate none | App | Passed
Phone app | documents.test.ts | the most recently reviewed check decides, like the server | App | Passed
Phone app | documents.test.ts | a pending check shows pending even after an approval | App | Passed
Phone app | documents.test.ts | a requirement code the app does not know still gets a row, after the known ones | App | Passed
Phone app | documents.test.ts | two services needing the same document give one row | App | Passed
Phone app | documents.test.ts | two different categories needing the same document give one row with the latest status | App | Passed
Phone app | documents.test.ts | a hidden service says a document is needed until it is uploaded, then that it waits for the check | App | Passed
Phone app | documents.test.ts | sharing is allowed only while no service waits for a document | App | Passed
Phone app | documents.test.ts | saving a waiting service keeps Share hidden: the server answer carries waitingFor | App | Passed
Use me | use-me.test.ts | a loadMe in flight at sign-out never fills the store for the next account | App | Passed
Contract | index.test.ts | ServiceInputSchema rejects three decimals and negative prices | Packages | Passed
Contract | index.test.ts | ServiceInputSchema needs no price on request | Packages | Passed
Contract | index.test.ts | AdminListQuerySchema caps pageSize at 100 | Packages | Passed
Contract | index.test.ts | parse helpers parseBody answers 400 with the issues | Packages | Passed
Contract | index.test.ts | parse helpers parseQuery reads the search params | Packages | Passed
Contract | index.test.ts | list envelopes lists are { docs: [...] } | Packages | Passed
Contract | index.test.ts | list envelopes reference year is checked against the current year at parse time | Packages | Passed
Contract | index.test.ts | address street, postcode and city are required (no empty or blank parts) | Packages | Passed
Contract | index.test.ts | service input as the app sends it a category alone is valid (the server fills currency and title) | Packages | Passed
Texts | index.test.ts | catalogue de and en have the same keys | Packages | Passed
Texts | index.test.ts | catalogue no text is empty and no two keys of one namespace carry the same text | Packages | Passed
Texts | index.test.ts | catalogue no text contains Treuhand, Escrow, garantiert or a competitor name | Packages | Passed
Texts | index.test.ts | catalogue the product name is only written in brand.name | Packages | Passed
Texts | index.test.ts | t replaces placeholders and falls back to the key when missing | Packages | Passed
Texts | index.test.ts | t fills the brand name without a parameter | Packages | Passed
Texts | index.test.ts | t knows its languages | Packages | Passed
Texts | index.test.ts | money formats per language | Packages | Passed
Texts | index.test.ts | money formats price labels from the catalogue | Packages | Passed
Texts | index.test.ts | acceptLang en-GB,en;q=0.9,de;q=0.8 -> en | Packages | Passed
Texts | index.test.ts | acceptLang * -> undefined | Packages | Passed
Texts | index.test.ts | acceptLang fr-FR -> undefined | Packages | Passed
Texts | index.test.ts | acceptLang -> undefined | Packages | Passed
Texts | index.test.ts | acceptLang undefined -> undefined | Packages | Passed

## Other Checks
Check | What it tested | Outcome | Notes
pnpm typecheck | All packages and apps compile with no type errors. | Passed | Run 27 October on registration-setup.
pnpm lint | ESLint over the whole repository. | Passed | Run 27 October.
pnpm test | The root test command (web, Docker database). | Passed | 35 files, 257 tests (the root run).
cd apps/mobile && npx tsc --noEmit | App code compiles. | Passed | Run 27 October.
Web integration tests on the Docker database | 35 spec files against local Postgres 17 + PostGIS. | Passed | 257 tests.
App tests (jest) | 20 suites. | Passed | 108 tests.
Package tests (contract, i18n) | 2 files. | Passed | 23 tests (contract 9, i18n 14).
cd apps/mobile && npx expo export --platform android | The Android bundle builds. | Passed | Run 27 October, exit 0.
Sign-up with names, address and picture, and the provider tick | Account is created, code confirmed, then names and address are saved, then the picture is uploaded, then the record is cleared. | Passed | apps/mobile use-session.test.ts (verify finishes the sign-up; a failed upload keeps the record); provider-profile.int.spec.ts (PATCH /me stores names and a private address).
Pending sign-up applies only to its own email | A saved sign-up record for another email is dropped and applies nothing. | Passed | apps/mobile use-session.test.ts (a record for another email is dropped); pending-signup.test.ts.
Setup page autosave | Two quick changes become one request; a failed save marks error and retries the same value; nothing typed is lost. | Passed | apps/mobile use-field-save.test.ts; serial-create.test.ts (one create per block); stale-guard.test.ts.
Publish rules and the missing list | An incomplete draft is 409 with the list; a complete one publishes with the public name; a draft is invisible; a suspended profile cannot publish. | Passed | provider-profile.int.spec.ts (missing list, publish, draft invisible in search and sitemap); publish-flow.int.spec.ts; apps/mobile profile-form.test.ts (every missing item has de and en text).
Services with a category only | A service with a category alone can be saved, and is never offerable or public. | Passed | rls-providers.int.spec.ts (a service with a category alone is never offerable); search.int.spec.ts; apps/mobile profile-form.test.ts.
Documents card | Rows per requirement, the latest check decides, pending shows pending, one row for a shared requirement. | Passed | apps/mobile documents.test.ts.
Share only without a pending check | Sharing is allowed only while no service waits for a document; the text and link follow the language. | Passed | apps/mobile documents.test.ts (sharing is allowed only while no service waits); share-profile.test.ts.
Profile-live email and banner | Email with the link and one notification; GET /me lists it; dismissing hides it; another user gets 404. | Passed | notifications.int.spec.ts; rls.int.spec.ts (notifications RLS); apps/mobile use-me.test.ts.
Email: document approved, profile live, nothing else pending | "Profile is live" with the link, plus a notification. | Passed | notifications.int.spec.ts.
Email: document approved, live, another document pending | Says the category service is visible, no notification. | Passed | notifications.int.spec.ts.
Email: document approved, profile offline | Offline text, no notification. | Passed | notifications.int.spec.ts (draft profile).
Email: document approved, profile suspended | Suspended text with the date, no notification. | Passed | notifications.int.spec.ts.
Email: document already approved, or not enough for any service | Plain approval, no notification. Rejection unchanged. | Passed | notifications.int.spec.ts.
Email: staff suspend the profile | Reason and end date in the user language. | Passed | admin-api.int.spec.ts (suspending a user).
Email: published again (lift and daily check) | One email when staff lift, one when the date passes. | Passed | admin-api.int.spec.ts; cron-suspensions.int.spec.ts.
Suspension ends by its date and the daily check | A past date shows the profile again without a lift; the cron clears both columns once; a future one is left alone; 401 without the secret. | Passed | admin-api.int.spec.ts; cron-suspensions.int.spec.ts; publish-flow.int.spec.ts (an ended suspension no longer blocks publishing).
Public name follows a rename | Changing the person's names changes the public name; slug unique and stable. | Passed | public-name.int.spec.ts.
Picture RLS: anonymous sees a live provider's picture only | A customer's, draft or suspended provider's picture is private; the search card carries the picture for anonymous callers. | Passed | rls.int.spec.ts (a person's picture is private until...); files-review.int.spec.ts; search.int.spec.ts (anonymous card).
Phone: sign-up screens and photo pickers | Names, address, picture and the provider tick on a real phone. | Not yet done (phone) | Owner.
Phone: one-page setup layout and keyboard behaviour | Fields stay visible above the keyboard; saves as you type. | Not yet done (phone) | Owner.
Phone: Share sheet | The phone's share sheet opens with the text and link. | Not yet done (phone) | Owner.
Phone: Account-tab dot | Dot shows for an unseen notification and clears once seen. | Not yet done (phone) | Owner.
Phone: home nudge | The nudge to set up a profile shows and can be dismissed. | Not yet done (phone) | Owner.
Migration 0008 on a database with data | Migrated to 0007 with a suspended provider, one without a date, published providers without names and pictures, then to 0008. | Passed | db-migrations.int.spec.ts: suspensions carried over, published ones back to draft. Also applied by hand on kando-dev (0 rows changed).
The app request shapes (fix wave 2) | Category-only service create, then one field per PATCH, with the exact bodies the app sends. | Passed | services-references.int.spec.ts (a category alone, one field per save; add and update answer with waitingFor).

## Open Items
Item | Detail | When
Phone checks: sign-up screens and photo pickers | Create an account with names, address, a picture and the provider tick; confirm the code. | Not yet done (phone)
Phone checks: one-page setup layout and keyboard | Each field saves as you type; the keyboard never hides the field. | Not yet done (phone)
Phone checks: Share sheet | Share opens the phone share sheet with the text and link. | Not yet done (phone)
Phone checks: Account-tab dot | The dot appears for the profile-live notification and goes after it is seen. | Not yet done (phone)
Phone checks: home nudge | The nudge shows and can be dismissed. | Not yet done (phone)
Fixed: emails on suspension and lift | Suspension and "published again" emails go only to a person who has a profile; a lift sends only when the user was suspended; the cron only emails people with a profile (a294569). | Fixed
Parked: end date in emails | Formatted in the server time zone, not the reader's. | Parked (minor)
Parked: cron emails sequential | The daily check sends its emails one after the other; fine for a few, slow for many. | Parked (minor)
Parked: owners can delete their own notifications | RLS allows the delete; harmless. | Parked (minor)
Parked: non-strict notification patch schema | PATCH accepts unknown fields (ignored). | Parked (minor)
Parked: concurrent approvals race | Two approvals at once can both send the email; harmless. | Parked (harmless)
Parked: tag text typed but not yet added | Saved on blur only. | Parked (minor)
Parked: invalid radius | Not persisted until it is valid. | Parked (minor)
Fixed (wave 2, minor 9): nudge-dismissed flag per user | The key carries the user id (107530c). | Fixed
Parked: Remove button flicker | The Remove button flickers while a queued update runs. | Parked (minor)
Missing tests | A failed create; the markNotificationsSeen and dismiss writers; two parallel draft POSTs. | Open
The radius item can never be in missing | The column default is 25, so it is never empty. | Known, accepted
Refine button labels still English | Save, Create, Edit, Delete stay English in both languages. | Known gap
Push notifications | Come with bookings; today the banner and the email are the only signals. | Later
Whole-branch review | Done. One Critical (service price could not be saved), two Important and the Minor points were fixed in a final fix wave; a scoped re-review follows. | Fixed, fix wave 2 done, re-review pending
Before shipping: CRON_SECRET on Vercel | Add it to Production (Vercel runs crons on Production only), or the daily check answers 401 and suspensions never end by date. | Owner, before ship
Before shipping: migration 0008 on any real database | pnpm db:migrate. It drops users.name, providers.display_name and the old profile photos. Dev is already migrated. Branch the database first. | Owner, before ship
Fixed (final review 1, Critical): service price | The price type and the price save in either order; a service counts only with a type and, unless on request, a price (completeness, offerable ids, search) (fd98b0b). | Fixed
Fixed (final review 2): live profile cannot be emptied | A save that would leave a published profile incomplete is refused with 409 and the missing list (eb614ff). | Fixed
Fixed (final review 3): staff and the picture | The provider page lists the person's picture and the user page has a Delete button for it (167b75d). | Fixed
Fixed (final review 5): country in the UI | Postcode lookup uses the owner's stored country, the setup postcode field is plain text, the Account save keeps the stored country (7616177). | Fixed
Fixed (final review 6): publish bar | A suspended profile shows the suspension, not Live (d815883). | Fixed
Fixed (final review 7): name required to publish | The missing list has "name" when first or last name is empty (eb614ff). | Fixed
Fixed (final review 8): picture key | The public picture key has a random folder, not the account id (d815883). | Fixed
Fixed (final review 9): Account screen | Changing the picture no longer resets unsaved name and address edits (7616177). | Fixed
Fixed (final review 10): docs | CRON_SECRET in .env.example; crons run on Production only; orphaned photo objects after migration 0008 are noted (585f274). | Fixed
Parked: one shared "not suspended" SQL constant | rls.ts policies now use the constant (wave 2); the SQL functions, search.ts, public-profile.ts, sitemap and TypeScript variants still write it out. | Parked (minor)
Fixed (wave 2, Critical): service create from the app | Currency is optional on create and defaults to EUR; the title defaults to the category name. Tested with the exact body { categoryId } then one-field PATCHes (af82e89). | Fixed
Fixed (wave 2, Important): add and update lose waitingFor | One helper gives waitingFor and visibleInSearch to list, add and update; Share stays hidden while a check is pending (af82e89). | Fixed
Fixed (wave 2, minor 4): suspension emails | Only published profiles get the suspension and published-again emails; the cron still clears every ended suspension (c033602). | Fixed
Fixed (wave 2, minor 6): Germany fallbacks | No DE fallback in shared server code; the provider column default applies without an address (b015bd7). | Fixed
Fixed (wave 2, minor 7, 8, 9): app | Sign-in sends only the language, sign-up ends with a /me reload, the nudge key is per user, dead updateName removed (107530c). | Fixed
Fixed (wave 2, minor 11): address | Street, postcode and city are required (cdc0958). | Fixed
Fixed (wave 2, minor 10): email link | App link uses the skilled scheme (d72c36c). | Fixed
Fixed (wave 2, minor 12): migration 0008 on real data | Suspended providers stay hidden; published ones without names or picture go back to draft; tested on a 0007 database with rows (5e965ac). | Fixed
Fixed (wave 2): simplification | rls.ts uses NOT_SUSPENDED; the price clause in search.ts is gone, offerable_service_ids covers it and the category search test proves it (34804f3). | Fixed
Parked: concurrent approvals | Two approvals at once can send the "profile is live" email twice. | Parked
Parked: last complete service of a live profile | Deleting or updating it is not blocked. | Parked
Parked: suspension check in TypeScript | Duplicated next to the SQL. | Parked
Owner question: My profile tab for customers | Should the tab be visible to customers? | Open (owner)