## Summary
Item | Detail
KANDO - Assessment fixes A to D: Combined Report
Branch / head | release/assessment-fixes at 927358f (PRs #35 to #38 merged into it; not yet merged into main). Verification run 31 October 2026 on the Docker test database (kando-db-1, port 5433). Remote databases untouched; pnpm db:migrate never run.
Source | Full-Project-Assessment-2026-10-30 (33 findings; baseline main 7617df9). Facts taken from the four stage reports and the SDD ledgers.
WHAT WAS FIXED
Stage A, PR #35, database connections and security | Findings 5, 6, 8, 15, 16, 17, 18, 19. Separate request and owner pools; one users write only when needed; Stripe, AI and upload calls outside the request transaction; migration 0022 (29 indexes, unique payment_ref, 17 CHECK constraints); app_status_guard trigger (only the answering side may accept or decline); translation tables staff-only; row-level security applied in one transaction; slug race fixed. 10 tasks (1 to 9 and 7b).
Stage B, PR #36, server flow and efficiency | Findings 2, 7, 21, 22, 23, 24, 25, 32 (and 6/7 carry-overs). Emails and pushes after the answer with outbox; four cron routes and retention; request withdraw and decline; provider dispute; reopen of a request after an unagreed quote booking; paged lists and read-one routes; SQL search with cached offerable flag; cached public pages; country-ready currency and search; migration 0023. 13 tasks (1 to 12 and 11b).
Stage C, PR #37, security | Findings 4, 9 (code part), 10, 11, 12, 14 (partly), 28, 29. Password to delete an account; cookie writes need Origin; private answers not cached; no writes on GET; contact-detail check on public texts; chat send limit; blocked-text purge after 90 days; upload Content-Length and 25 MP cap; HSTS includeSubDomains and report-only CSP with script-src; back office provider read without payment and tax fields. 11 tasks (1 to 10 and 12; Task 11 not done by ruling).
Stage D, PR #38, mobile flow and clean-up | Findings 1, 3 (partly), 20, 26, 27, 30, 31. Pay card knows if payments are on and the pay path is tested end to end; Open buttons on every booking notice, notices on Home and My bookings; Account shows failures with Retry; busy login server is a 503 not a sign-out; ellipsis; button gaps; shared constants and helpers; app bundle 52,868 B smaller, test hooks behind a testing entry. 12 tasks.
Tasks / findings | Tasks: A 10, B 13, C 11, D 12 = 46. Findings: 33 in the assessment; see Findings sheet for the status of each.
COMBINED VERIFICATION (this head)
Web tests | 849 passed of 849 in 83 files, 0 failed
@kando/domain | 240 passed of 240 in 9 files
@kando/contract | 22 passed of 22 in 4 files
@kando/i18n | 18 passed of 18 in 1 file
Mobile (jest) | 313 passed of 313 in 53 suites
Total tests | 1442 tests, 0 failed (web 849, domain 240, contract 22, i18n 18, mobile 313)
Typecheck (tsc --noEmit) | web, db, domain, contract, i18n clean; mobile only the 4 known older typed-route errors
Lint | 38 errors (older, outside the product), 0 new
Known flakes | None occurred in this run (admin-roles last Administrator, auth-cookie-flow, email language fallback all passed); no rerun needed.
MERGE AND DEPLOY STATE
Merged | Stage PRs #35, #36, #37, #38 are merged into release/assessment-fixes. release/assessment-fixes is NOT merged into main.
Production code | Not promoted. main is still the Phase 2 release 7617df9.
Production database (kando-main) | At migration 0021. Migrations 0022 and 0023 and the row-level-security changes are NOT applied (deliberate: apply before promoting the code; see Release Checklist).
Dev database (kando-dev) | At 0023 with rls.ts re-applied at the end of Stage C. Stage D changed no database.
NOT DONE (honest list)
1 | Nothing from Stages A to D has been seen on a phone or on a Vercel Preview. All phone and real-service checks are open (A 3, B 6, C 5, D 11 as listed in the stage reports; many overlap, see Owner Actions).
2 | Finding 13 (Preview shares live keys) and finding 33 (dashboard-only checks) are owner dashboard actions; nothing was done in code.
3 | Finding 14 is partly done: script-src is report-only. Enforcing it needs the owner console walkthrough of the preview, then a one-line change (Stage C Task 11 not done).
4 | Finding 9: only the code part (chat send limit) is done. WAF rate-limit rules and a body-size rule are the owner dashboard (plan check).
5 | Finding 12: the 411 rule awaits the phone upload check (if an upload answers 411, one line is removed).
6 | Finding 4: the password check awaits a real account deletion on the preview with Neon Auth.
7 | Inbox and "tentative" booking (owner item 5) is NOT built; a design talk is needed first. Stage D only adds Open buttons and notices on Home and My bookings.
8 | attachDatabasePool (@vercel/functions) not added (owner decision pending); pools use limits and error logging instead.
9 | No trial of migration 0022 on a copy of production (owner decided against); read-only pre-checks found 0 violating rows on kando-dev and kando-main.
10 | German texts are not read by a native speaker; retention periods (180/90/270 days, 90-day contact text) are proposals awaiting the owner.
11 | No component tests for the Stage D screens (Home, My bookings, Account, notify-me card); logic is tested in plain functions.
12 | Second market (South Africa) not started: the phone does not send a country yet.

## Findings
# | Priority | Area | Finding | Status | Stage and PR | What changed | Which test proves it | Remaining owner step
1 | 1 Critical | Flow | With payments off no booking can ever reach 'confirmed'. Pay now ends in 'payments are off'; cancel, start, finish, confirm, dispute, review and invoices are unreachable in the app. | Fixed, owner check pending | D, PR #38 (Tasks 1, 2) | /me carries paymentsEnabled; pay, notify-me and payout cards read it from the start so no pay button fails; the pay path is walked through the route handlers in a test; payments:smoke step e checks the webhook URL; README Stripe steps 11 to 14. Production stays payments-off by design. | payments.int.spec.ts (pay link, paid event, booking reads confirmed, repeat event); me route spec; mobile payments-off tests (5) | Stripe test-card walk on Android on a test build; decide what production shows while payments are off.
2 | 2 High | Flow | Propose new time: a declined, expired or withdrawn proposal sets the request to 'booked' for good. Customer cannot retry, provider cannot re-quote; the job is lost. | Fixed, owner check pending | B, PR #36 (Task 5); C, PR #37 (Task 4) | Trigger reopens the request (booked to quoted) and the quote (to sent, or expired) when a quote-born booking is declined, expires or is withdrawn; customer gets request reopened; in Stage C a lapsed proposal reopens at once when someone accepts or sends a quote. | Reopen specs in timers.int.spec.ts and bookings.int.spec.ts; rls-bookings.int.spec.ts (trigger) | Phone check: reopened quote after an unagreed booking.
3 | 3 High | Flow | Booking notices (proposed, accepted, declined, expired) have no Open button; they show only as text on the Account tab. | Partly | D, PR #38 (Task 3) | Every booking notice has an Open target and button; notices also show on Home and My bookings; the request-reopened push opens the request screen. The inbox is NOT built. | mobile notification-text.test.ts (13); push-send.int.spec.ts | Phone check of Open buttons; inbox / tentative booking design talk (owner item 5).
4 | 4 High | Security | Account deletion needs only the account's own email: anyone holding a logged-in phone can erase the account. | Fixed, owner check pending | C, PR #37 (Tasks 1, 2) | DELETE /me takes the password; server checks it with a throw-away sign-in at Neon Auth (wrong gives 403 WRONG_PASSWORD, busy gives 503 AUTH_BUSY); the phone asks for the password and shows its own texts. | verify-password.int.spec.ts; account-delete.int.spec.ts; mobile account-data, api/account, i18n errors tests | Real account deletion on the preview with Neon Auth, wrong and right password.
5 | 5 High | Database | Connection pool has no size limit or error handler; one request often holds two or three connections, so concurrent requests can run dry and time out after 10 s. Network calls (OpenRouter, S3, Stripe) run while a transaction is open. | Fixed, owner check pending | A, PR #35 (Tasks 1, 3, 5) | Separate request and owner pools with limits, 5 s idle timeout and error logging; Stripe, Neon Auth, AI calls and uploads run outside the request transaction. attachDatabasePool not added (no new dependency); settle stays under the booking lock by design. | db-pool, concurrency, owner-connection, app-request, files and payments specs | Owner phone/preview load check (chat polling from two phones, no 10 s timeouts); decide on attachDatabasePool.
6 | 6 High | Efficiency | Every request makes about four extra round trips and rewrites the users row (also chat polling every 4 s). | Fixed | A, PR #35 (Task 2) | users sync: SELECT first, UPDATE only when the email changed, INSERT ... ON CONFLICT only for a new user; Neon Auth lookup cached. | app-request.int.spec.ts (unchanged email not rewritten); auth-cookie-flow; account-delete
7 | 7 High | Efficiency | Emails and pushes are sent before the answer is returned; Resend has no timeout; the daily job can lose emails when cut off at 60 s. | Fixed | B, PR #36 (Tasks 2, 3) | Emails and pushes queued and sent after the answer (after()); Resend 10 s timeout, never throws; timer notices written unsent and drained by an outbox (48 h limit). | deferred-sends and email specs; cron-bookings.int.spec.ts; timers.int.spec.ts
8 | 8 High | Database | About 15 foreign-key/search columns have no index (threads, messages.sender_id, blocks, bookings.service_id, providers.location GiST, cron status/deadline columns). | Fixed | A, PR #35 (Task 6) | Migration 0022: 29 indexes (including the providers location gist and partial ones). In dev; kando-main still at 0021. | db-migrations.int.spec.ts (0022 creates every listed index) | Apply 0022 to kando-main at release (Release Checklist step 2).
9 | 9 Medium | Security | No rate limit on login, chat, uploads, signed links, search, payout setup. | Partly | C, PR #37 (Task 6) | Code part done: at most 30 text or photo messages in 10 minutes per user (429 MESSAGE_LIMIT, no object stored). Network rate limits are not code. | chat-safety.int.spec.ts (31st refused; 31 parallel sends store 30); mobile errors.test.ts | Vercel firewall rate-limit rules for sign-in, chat, uploads, public-text saves (check plan).
10 | 10 Medium | Security | Contact-detail blocking misses public profile text, names, service text, references and chat photos, so contact details can leak and skip the commission. | Fixed, owner check pending | C, PR #37 (Task 5) | The chat matcher runs on profile, service, reference, name and photo texts; 422 CONTACT_DETAILS; public-text refusals do not count toward the staff flag; a refused sign-up name is dropped. Chat photos remain a known limit. | contact-public.int.spec.ts; mobile use-session.test.ts | Phone check: profile text with a phone number; refused sign-up name.
11 | 11 Medium | Security | A read-only Reviewer sees providers' Stripe account id, tax number, VAT id. | Fixed | C, PR #37 (Task 10) | Back office provider read returns an explicit field list without Stripe account, payout, tax, VAT, legal status, invoice consent or location fields. | admin-api.int.spec.ts, admin-roles.int.spec.ts, admin-chat.int.spec.ts
12 | 12 Medium | Security | Uploads are fully buffered before the size cap; a missing Content-Length is accepted. | Fixed, owner check pending | C, PR #37 (Task 8) | Upload routes need Content-Length (411 otherwise); a declared length over the cap is 413; the body is counted while read and cut at the cap; pictures over 25 MP refused (was 40). | app-request.int.spec.ts (411, endless body 413, over cap 413); files.int.spec.ts (25 MP) | Android upload check (photo, PDF, scan, chat photo); if 411, remove one line. Decide on the 25 MP limit for large document scans; WAF body-size rule.
13 | 13 Medium | Security | Preview builds share live storage, email and cron keys with Production. | Not done: owner action | None | Vercel dashboard setting; nothing changed in code. | Not applicable | Untick Preview on live storage, email and cron keys; add Preview test values; Stripe key test-only on Preview.
14 | 14 Medium | Security | Content-Security-Policy has no script-src. | Partly | C, PR #37 (Task 9) | HSTS max-age 2 years with includeSubDomains; Content-Security-Policy-Report-Only with script-src sent next to the enforced policy. Enforcing script-src (Task 11) not done. | security-headers.int.spec.ts | Console walkthrough of the preview, then a one-line enforce; confirm no HTTP-only subdomain.
15 | 15 Medium | Database | Row policies let either side edit more booking/request/quote columns than the domain allows (pay_by, answer_by, status). Safe today only because the code behaves. | Fixed | A, PR #35 (Tasks 7, 7b) | app_status_guard trigger on requests, quotes and bookings: the app role makes only the moves in APP_STATUS_MOVES on the right side; pay_by, accepted_at and proposal columns move only with their transition; only the answering side may accept or decline (self-accept refused). | rls-bookings.int.spec.ts (status moves, self-accept for both sides with positive controls) | Apply to kando-main at release (re-apply rls.ts).
16 | 16 Medium | Database | translation_requests is readable by everyone and writable with any key (rate-limit poisoning). | Fixed | A, PR #35 (Task 4) | translations read-only for the app role; translation_requests staff-only; the translate route writes on the owner connection after the transaction. | rls.int.spec.ts (app_user cannot read or write translation_requests); translate, provider-translation, provider-page specs | Apply rls change to kando-main BEFORE promoting code (step 2).
17 | 17 Medium | Database | Money tables have thin constraints: no unique payment_ref, no range checks, free-text currency. | Fixed | A, PR #35 (Task 6) | Migration 0022: unique bookings.payment_ref and 17 CHECK constraints (amounts, commission rate, currency, duration). Pre-check: 0 violating rows on kando-dev and kando-main. | rls-payments.int.spec.ts (payment_ref 23505, currency, amounts, commission rate, zero duration) | Apply 0022 to kando-main at release.
18 | 18 Medium | Database | Migration steps are not atomic: applyRls runs about 150 statements one by one (brief permission gaps); status/kind CHECK changes lock notifications. | Fixed | A, PR #35 (Task 8) | applyRls runs all statements in one transaction (all or nothing). | rls.int.spec.ts (applyRls is all or nothing)
19 | 19 Medium | Database | Two providers publishing the same name can collide on the slug (500). | Fixed | A, PR #35 (Task 8) | Slug assignment takes pg_advisory_xact_lock so two providers with the same name publishing at once both succeed. | publish-flow spec (two providers publish at once; was [500, 200])
20 | 20 Medium | Flow | Account screen hides failures: if /me fails nothing shows, and the 'Offer services' error text sits inside the loaded-only block with a generic message. Likely source of the owner's error. | Fixed, owner check pending | D, PR #38 (Tasks 4, 5) | Account keeps the load error and shows Retry; Offer-services failure has its own text; a busy Neon Auth answers 503 AUTH_BUSY instead of signing out (also for the back office). | session spec; app-request.int.spec.ts (AUTH_BUSY); require-staff test; mobile start-offering.test.ts (9) | Retest Offer services on the Preview with the Vercel log; airplane-mode and busy-login phone checks.
21 | 21 Medium | Efficiency | No list has a limit or pagination; opening one booking/chat downloads whole lists; no read-one routes. | Fixed | B, PR #36 (Tasks 7, 8) | Lists return pages of 50 with a strict cursor (forged cursor 400); read-one booking and thread routes; phone shows Show more. | bookings, requests, threads list specs; contract tests; mobile api and list tests | Phone check: Show more.
22 | 22 Medium | Efficiency | Search recomputes 500 candidates per page, drops providers beyond 500, labels everyone 'new'. | Fixed | B, PR #36 (Task 9) | Search pages in SQL; services.offerable cached flag kept by triggers; cards show ratings. | search.int.spec.ts; rls.int.spec.ts (offerable triggers) | Confirm the name sort order (lower(name)).
23 | 23 Medium | Efficiency | Public site pages are rendered per visitor (layout reads headers()). | Fixed | B, PR #36 (Tasks 11, 11b) | Public pages live under /[lang], static with revalidate 300 or 3600; changes call revalidatePath. | proxy, home-page, provider-page, pages, sitemaps specs
24 | 24 Medium | Efficiency | Daily cron does everything in one function with one 30 s budget; a backlog can starve commission invoices; some tables are never cleaned up. | Fixed, owner check pending | B, PR #36 (Task 3) | Four cron routes (03/04/05/06 UTC) each with its own budget; retention removes seen notices after 180 days, processed Stripe events after 90, device tokens after 270 (proposals). | cron-*.int.spec.ts; retention spec; timers.int.spec.ts | Plan must allow four cron jobs; confirm retention periods.
25 | 25 Medium | Flow | A request cannot be withdrawn by the customer or declined by the provider; the provider cannot open a dispute from the UI (README says either side). | Fixed, owner check pending | B, PR #36 (Tasks 4, 6, 8) | Customer withdraws and provider declines a request; either side may open a dispute after Finished or Stop; phone buttons with confirmation. | requests-quotes.int.spec.ts; disputes.int.spec.ts; rls-bookings.int.spec.ts; mobile request-detail and booking-status tests | Phone checks: withdraw, decline, provider dispute.
26 | 26 Low | Flow | Invalid byte shows as a question mark in the service editor. | Fixed | D, PR #38 (Task 6) | Invalid byte replaced by the real ellipsis; a test scans every app source file for invalid UTF-8. | mobile source-encoding.test.ts
27 | 27 Low | Flow | Smaller button gaps: notify-me starts 'off'; resend code has no busy state; accept/Book taps can double-push; admin sign-in errors always German. | Fixed | D, PR #38 (Tasks 6, 7, 8) | Resend busy state; one navigation per tap; notify-me starts from the saved state; back-office sign-in errors in the back-office language; rating shown once. | mobile go.test.ts; payouts.int.spec.ts (watching); admin lang and auth-provider tests (12)
28 | 28 Low | Security | Origin guard passes requests with no Origin header; GET lists change state; private-link responses lack no-store; blocked-contact text stored forever; admin user id not validated; internal ids exposed. | Fixed | C, PR #37 (Tasks 3, 4, 7, 10); D, PR #38 (final fix 8733c34) | (a) cookie write without Origin is 403; (b) no writes on GET (lapsed items shown as expired, reopen on the write paths); (c) private answers carry Cache-Control private, no-store including thrown, busy and early answers; (d) blocked contact text purged after 90 days; (e) admin user id validated. Customer ids visible to providers accepted. | origin-check.int.spec.ts; app-request.int.spec.ts; timers.int.spec.ts; cron-suspensions.int.spec.ts; admin-api.int.spec.ts | Confirm the 90-day keep period.
29 | 29 Low | Security | Cron route 'suspensions' has no maxDuration; HSTS lacks includeSubDomains; .env.example misses keys. | Fixed, owner check pending | C, PR #37 (Tasks 7, 9) | maxDuration on the suspensions cron; .env.example lists every variable the code reads (tested); HSTS includeSubDomains. | cron-suspensions.int.spec.ts; env-example.int.spec.ts; security-headers.int.spec.ts | Confirm no HTTP-only skillweb.space subdomain; check the live HSTS header.
30 | 30 Low | Duplication | Cron secret check copied twice; partyOf/sideOf and lockRow duplicated; notFound/HOUR/DAY/NO_ID redefined in 15 files; cancellation constants copied into the mobile app. | Fixed | D, PR #38 (Task 9) | HOUR, DAY, FREE_CANCEL_HOURS, STOP_ANSWER_DAYS, LATE_CANCEL_SHARE, NO_SHOW_OBJECTION_HOURS live once in @kando/contract; booking helpers once in the domain package. | contract endings.test.ts; booking, cancel, finish, disputes, timers and admin specs
31 | 31 Low | Efficiency | Mobile ships 311 admin/email texts it never shows; the domain barrel exports test hooks (bundle size unmeasured). | Fixed | D, PR #38 (Tasks 10, 11) | Measured first (49,036 B = 1.2 % of 4,081,887 B): app ships only its own texts (@kando/i18n/app); bundle 52,868 B smaller; domain test hooks behind a testing entry. | i18n index.test.ts (18); mobile i18n tests; 36 web specs switched
32 | 32 Low | Country-ready | Quote currency EUR and search country DE are hard-coded. | Fixed | B, PR #36 (Tasks 1, 10) | Quote currency comes from the provider country (migration 0023 adds countries.currency); search takes the country from the request; sitemaps list all markets. | requests-quotes, search and sitemaps specs (second market ZZ) | Later: the phone must send a country when a second market launches.
33 | 33 Info | Hosting | Items only the dashboards can show: preview database branch, Stripe key prefix, bypass secret, fork-PR protection, build-log exposure, cron runs, Neon Auth cookie flags and login limits, staff second factor. | Not done: owner action | None | Dashboard-only checks; nothing in code. | Not applicable | Preview database branch, Stripe key prefix, bypass secret, fork-PR protection, build-log exposure, cron runs, Neon Auth cookie flags and login limits, staff second factor.

## Test Results
Suite | Command | Files / suites | Tests | Passed | Failed | Skipped | Notes
Web (vitest) | pnpm --filter web test | 83 | 849 | 849 | 0 | 0 | One run, one process, Docker test DB (port 5433). No flake occurred; no rerun needed. Duration 518 s.
@kando/domain | pnpm --filter @kando/domain test | 9 | 240 | 240 | 0 | 0
@kando/contract | pnpm --filter @kando/contract test | 4 | 22 | 22 | 0 | 0
@kando/i18n | pnpm --filter @kando/i18n test | 1 | 18 | 18 | 0 | 0
Mobile (jest) | pnpm --filter mobile test | 53 | 313 | 313 | 0 | 0 | 53 suites
Total |  | 150 | 1442 | 1442 | 0 | 0 | Stage D report on its head: 847 + 238 + 309 + 22 + 18 = 1434; the added 8 are tests added after the Stage D report (final review fix wave: web +2, domain +2, mobile +4).
Typecheck and lint
tsc apps/web | npx tsc --noEmit | [5 empty] | Clean (exit 0)
tsc apps/mobile | npx tsc --noEmit | [5 empty] | 4 errors, all the known older typed-route errors (about-card.tsx, documents-card.tsx, services-card.tsx x2); none new
tsc packages/db, domain, contract, i18n | npx tsc --noEmit | [5 empty] | Clean (exit 0) in each
pnpm lint | pnpm lint | [5 empty] | 38 errors, 0 warnings: the same 38 older errors, all in .work/scripts/make-admin.js and Marketing/tools/*.mjs/js (outside the product). None new, so no lint fix commit.

## Review Log
Stage | Scope | Tasks | Review rounds | Important or critical findings and how each was fixed | Final review fix wave and other
A | Database connections and security (PR #35) | 10 (1 to 9, 7b) | Every task reviewed once by an independent reviewer, all clean; final review, one fix wave (d6ec54d), re-review clean. | Important (task review of 7): the database did not check whose turn it was, so a customer could accept their own proposal and a provider their own counter (self-accept gap; the brief had said "either"). Fixed by Task 7b (d4affd0..92e557e): side kind "answerer", counter_by logic in the trigger, with positive controls in rls-bookings.int.spec.ts. | Final review fix wave d6ec54d: booking address frozen after the proposal, accepted_at bounded, owner handles kept out of the package index, wording of the Stage A claim about network calls corrected. Minors deferred (see Open Items).
B | Server flow and efficiency (PR #36) | 13 (1 to 12, 11b) | Per-task reviews clean (Task 11b added by ruling after Task 11); final review, two fix commits (f496bfc, 05d3c0c), re-review clean. | Important (final review): the services.offerable flag could go stale in a race between a new service or document change and the owner lock; closeRequest answered 500 when the timers expired the request after the read; stale payment and quote reminders could still be sent from the outbox; payouts/status refreshed all public pages on every call. Task 11b added because endings (confirm, cancel, stop, dispute) still settled and notified inside the transaction and reviews/admin edits did not refresh public pages. | f496bfc: offerable race fixed with the owner advisory lock and a share lock on the category; closeRequest updates only open or quoted requests (409 request-closed); outbox claims but does not send reminders of closed items; payouts/status refreshes only when stored readiness changed. 05d3c0c: exact Stripe transaction wording in README, final release checklist, timers comment.
C | Security (PR #37) | 11 (1 to 10, 12; Task 11 not done) | Tasks 1, 3, 6 to 10 clean first time; Tasks 2, 4 and 5 needed one fix round each (re-reviews clean); final review, one fix wave (dc8b6f6). | Task 2: the phone showed "deletion unconfirmed" for 503 AUTH_BUSY (fixed: busy text, no check call). Important, Task 4: reopening a lapsed proposal only on the daily cron could lose the job, and conflicted with finding 28b (no writes on GET). Fixed by ruling: reads stay write-free but show the reopened view; acceptQuote and sendQuote expire the single lapsed quote-born booking under their locks through an owner-connection helper so the trigger reopens at once (reopen-vs-read conflict). Important, Task 5: (1) false positives on opening hours or postcode lists counted toward the staff flag; (2) sign-up names refused with 422 failed silently and retried forever. Fixed: public-text refusals do not count toward the flag; a refused sign-up name is dropped from the pending data. | dc8b6f6: busy-path log, LENGTH_REQUIRED text in the phone, extra tests, finding labels. Task 11 (enforce script-src) not done by ruling: needs the owner console walkthrough.
D | Mobile flow and clean-up (PR #38) | 12 | Per-task reviews clean (Task 8 read by the controller); final review, two fix commits (8733c34, ddb84ac), re-review clean. | Important (final review): a busy login server (429/5xx from get-session) at app start showed the login form instead of Retry (launch busy path); thrown, busy and early answers skipped Cache-Control private, no-store (finding 28c carry-over). | ddb84ac: 429 or 5xx from get-session sets offline (cookie kept; only 401 signs out); notice target uses shared request-screen kinds from @kando/contract; notify-me follows its watching prop; late-fee and 24 h boundary tests. 8733c34: one local helper in app-request and admin-request adds Cache-Control private, no-store to thrown, busy and early answers. Task 12 also fixed one real test failure (env-example: VERCEL_AUTOMATION_BYPASS_SECRET missing from .env.example).
All | Pattern | 46 tasks | Number of review rounds per task is not recorded beyond the above; the ledgers record "review clean" or "fix round n". | Not recorded: a count of minor findings (they are listed per task in the ledgers and the stage Open Items).

## Release Checklist
Step | What | Detail | Who | Done
1 | Check the countries on production | Run SELECT code FROM countries on kando-main. Expect only DE (migration 0023 adds a currency column and the code takes the currency from the country). | Owner / controller | [ ]
2 | Apply migrations and re-apply row-level security BEFORE promoting code | Apply 0022 and 0023 to kando-main and re-apply rls.ts: pnpm db:migrate against kando-main with the direct (unpooled) connection string. Do it first: the rls change makes translation_requests staff-only, and the old code on main would lose translations; the new code writes them on the owner connection. kando-main is at 0021 today. (Pre-check found 0 rows violating the new constraints on kando-main.) | Owner | [ ]
3 | Merge release/assessment-fixes into main | One pull request, owner merges. | Owner | [ ]
4 | Verify the Vercel deployment | Deployment finished and healthy; cron jobs: four entries (bookings 03:00, money 04:00, invoices 05:00, suspensions 06:00 UTC) and the plan allows four; Stripe webhook answers 400 as JSON (payments:smoke step e); security headers served (HSTS includeSubDomains, enforced CSP, Report-Only CSP with script-src, no-store on private answers). | Owner | [ ]
5 | Owner phone checks | Android first (iPhone later): delete account with wrong and right password; uploads (portfolio photo, document as PDF and as photo/scan, chat photo; if 411 remove one line); Stripe test card walk (only on a test build); withdraw and decline a request; provider dispute; reopened quote; Show more on the lists; rating on search cards; Open buttons on Home, My bookings and Account; Account with airplane mode; Offer services retest with the Vercel log; chat polling from two phones (no 10 s timeouts). | Owner | [ ]

## Owner Actions
Action | What to do | Relates to
Vercel: Preview keys | Untick Preview on the live storage, email and cron keys and give Preview test values (finding 13). Check the Stripe key prefix: test only on Preview. | Finding 13
Vercel: firewall | Rate-limit rules for sign-in, chat sending and the public-text saves, and a maximum request body size. Check that the plan allows them. | Findings 9, 12
Neon: storage key | A Neon storage access key for kando-dev. | Stage A/D
Stripe: Preview webhooks | Webhook for the protected Preview with the protection bypass (x-vercel-protection-bypass; the smoke script reads VERCEL_AUTOMATION_BYPASS_SECRET). | Stage D Task 2
HSTS | Confirm skillweb.space has no HTTP-only subdomain (includeSubDomains for 2 years) and look at the live header (Vercel adds its own HSTS without includeSubDomains). | Finding 29
Vercel plan: cron | Confirm the plan allows four cron jobs; on the free plan they run daily (payment reminders effectively off until the booking timer is hourly on Pro). | Finding 24
Hosting-audit dashboard checks | Preview database branch, Stripe key prefix, bypass secret, fork-PR protection, build-log exposure, cron runs, Neon Auth cookie flags and login limits, staff second factor. | Finding 33
Inbox and tentative booking | Design talk (Q&A) before anything is built. | Owner item 5
CSP console walkthrough | Open the preview with the browser console open, walk the pages listed in the Stage C plan, look for Content-Security-Policy-Report-Only violations; if none, enforce script-src with a one-line config change. | Finding 14
Phone checks Stage C | Delete account (wrong and right password); uploads (see Release Checklist 5); profile text with a phone number shows the contact-details text; a refused sign-up name is dropped. | Findings 4, 10, 12
Phone checks Stage D | Stripe card walk on Android (4242..., declined 4000 0000 0000 0002, 3-D Secure 4000 0027 6000 3184); Open buttons; airplane mode; Offer services retest with the Vercel log; a busy login server is not a sign-out. | Findings 1, 3, 20
Phone checks Stage B | Withdraw, decline, provider dispute, reopened quote, Show more, rating on cards. | Findings 2, 21, 22, 25
Native read of German texts | New German texts (request withdrawn, declined, reopened, dispute reason, buttons, new errors) need a native reader; known polish: "Deine" mid-sentence, a colon. | Stage B/C/D
Retention periods | Confirm or change: notices 180 days, Stripe events 90 days, device tokens 270 days, blocked contact text 90 days (open flags keep their rows). Tell the lawyer. | Findings 24, 28d
25 MP document limit | The 25 megapixel cap also refuses large document scans (a 600 dpi A4 page is about 35 MP, shown as "Unsupported file type"). Raise the document limit separately if needed. | Finding 12
attachDatabasePool | Say yes to add the @vercel/functions dependency (one import, one call per pool) or leave as is. | Finding 5
Name sort order | Search sorts names by lower(name); confirm that order (umlauts follow the database collation). | Finding 22
Production request rules | Decide what production shows while payments are off (hide the pay area and say so, or stop at accepted); Stripe test mode on Preview walks the whole flow. | Finding 1

## Open Items
Item | Source | What it costs if ignored / note | Owner decision or when
Inbox and "tentative" booking not built | Owner item 5 | Only Open buttons and notices on Home and My bookings exist. | OWNER DECISION: design talk, then a later stage
Enforce script-src (Stage C Task 11) | Finding 14 | Policy stays report-only; no report endpoint (violations only in the browser console). | OWNER: console walkthrough
Nonce policy for /admin | Stage C Task 9 | Only a ponytail comment in next.config.ts. | Later
WAF rate limits and body-size rule | Findings 9, 12 | Chat has a per-user limit; refused public-text saves have none (and are not counted for the flag). | OWNER: Vercel dashboard
Neon Auth login limits are shared | Stage C Task 1 | Upstream sees the server IP; no per-person limit; a per-user attempt counter would need a table. | Later / owner decision
Expiry and reopen notices come with the cron run | Stage C Task 4 ruling | A lapsed item shows expired at once, its notice comes with the cron (daily on the free plan). A lapsed proposal reopens at once when someone accepts or sends a quote. | Owner: plan
Retention periods 180 / 90 / 270 days; 90-day contact text | Stages B, C | Proposals set in code. | OWNER DECISION
Four cron jobs and plan limit | Stage B | Plan must allow four; payment reminders effectively off until hourly (Pro). | OWNER check
25 MP cap refuses large document scans | Stage C Task 8 | See Owner Actions. | OWNER DECISION
Chat photos not checked for numbers | Stage C Task 5 | Known limit; public texts are checked. | Known limit
Customer ids visible to providers | Stage C Task 10 | Accepted. | Accepted
attachDatabasePool not added | Stage A | Pools use limits and logging. | OWNER DECISION
Stripe refund and transfer stay under the booking lock; admin decideDispute and staffRefund settle in the admin owner-pool transaction | Stages A, B | By design; low volume; moving needs an after-transaction step in adminRequest. | Later
Chat photos stored inside the transaction; orphan objects on process death (no sweeper); invoice PDFs inline | Stage A | Move with Inngest or later. | Later
Cancel and stop notices can be lost if the read-only COMMIT fails after step 1 | Stage B 11b | The timer retries the money. | Later
Search seq-scans providers when a radius is used | Stage B Task 9 | works_remotely OR ST_DWithin; constant-distance prefilter plus UNION later. Partial indexes for notifications.mailed_at and services.offerable not added. | Later
Mobile must send a country when a second market launches; other DE/EUR literals remain | Stages B, D | Search is 400 without a country once two markets exist. | Second market (later)
Public website caching minors | Stage B Task 11 | 404 pages cached; odd URLs skipped by the matcher get a bare 404; /translated reachable directly; webhook refreshAccount does not refresh public pages. | Later
Customer declining a counter reopens silently | Stage B Task 5 | Provider not told. | Later
acceptQuote emails request-reopened about the customer's own action | Stage C Task 4 | Self-notice. | Later
Stage A/B/C/D deferred minors | Ledgers | Listed per task in the four stage reports (Open Items sheets) and in .superpowers/sdd/*/progress.md: e.g. update branch returns no row if user deleted between SELECT and UPDATE; address columns editable while proposed; answer_by unbounded on a counter; outbox: confirm-reminder not stale-checked; same-owner provider reassignment deadlock note; resetPaymentsOff not called on sign-out; README step 11 stripe listen lacks --forward-connect-to; admin screens show a generic error for 503. | Later
No component tests for Home, My bookings, Account, notify-me | Stage D | Covered by phone checks. | Owner phone test
Test Results counts | Stage C note | The Stage C sheet lacks 3 later tests; the Test Results sheet here recounts on the final head. | Done here