## Summary
KANDO full project assessment, 30 October 2026
Scope | Architecture and duplication, Neon database, Next.js code security, Vercel hosting security, buttons and process flows (read-only).
Baseline | main 7617df9 (Phase 2 release)
Critical | 1
High | 7
Medium | 17
Low | 7
Info | 1
Code changes made | None. Findings only; fixing is the owner's decision.

## Findings
# | Priority | Area | Finding | Where | Corrective action | Owner decision needed
1 | 1 Critical | Flow | With payments off no booking can ever reach 'confirmed'. Pay now ends in 'payments are off'; cancel, start, finish, confirm, dispute, review and invoices are unreachable in the app. | payments/webhook.ts:81; bookings/[id]/pay/route.ts; booking-status.ts:91-109 | Run Stripe test mode on Preview/test builds so the whole flow can be walked through. For production decide: hide the pay area and say so, or stop at 'accepted'. | Yes
2 | 2 High | Flow | Propose new time: a declined, expired or withdrawn proposal sets the request to 'booked' for good. Customer cannot retry, provider cannot re-quote; the job is lost. | bookings/requests.ts:254; bookings.ts:102; timers.ts:99-110 | When a quote-born booking ends declined/expired/withdrawn, set the request back to 'quoted' and the quote to 'sent' (if not expired) and tell the customer. | Confirm behaviour
3 | 3 High | Flow | Booking notices (proposed, accepted, declined, expired) have no Open button; they show only as text on the Account tab. | mobile lib/notification-text.ts:71-77 | Add an Open target for every booking notice (bookingId/requestId is in the payload); show notices on Home/My bookings. Fits owner fix list items 3-5. | Design talk (inbox)
4 | 4 High | Security | Account deletion needs only the account's own email: anyone holding a logged-in phone can erase the account. | me/route.ts:252; account.ts:104 | Require the password or a fresh login/email code before deleting. Before launch. | No
5 | 5 High | Database | Connection pool has no size limit or error handler; one request often holds two or three connections, so concurrent requests can run dry and time out after 10 s. Network calls (OpenRouter, S3, Stripe) run while a transaction is open. | packages/db/src/client.ts:33; app-request.ts; translate.ts; photos.ts; documents.ts; settle.ts | Set max, add pool.on('error'), use attachDatabasePool; do not use a second connection per request; move model and storage calls outside the transaction. | No
6 | 6 High | Efficiency | Every request makes about four extra round trips and rewrites the users row (also chat polling every 4 s). | users.ts:49-64 (ensureUser) | Cache the to_regclass check; update only when the email changed; use RETURNING instead of the extra SELECT. | No
7 | 7 High | Efficiency | Emails and pushes are sent before the answer is returned; Resend has no timeout; the daily job can lose emails when cut off at 60 s. | app-request.ts:71; email.ts:108; timers.ts:324 | Run after-commit work with after(); add a timeout; keep a small outbox the cron drains within its budget. | No
8 | 8 High | Database | About 15 foreign-key/search columns have no index (threads, messages.sender_id, blocks, bookings.service_id, providers.location GiST, cron status/deadline columns). | schema/chat.ts, bookings, providers | One migration with CREATE INDEX CONCURRENTLY (SQL in the database audit). Test on a branch of kando-main first. | No
9 | 9 Medium | Security | No rate limit on login, chat, uploads, signed links, search, payout setup. | threads/*/messages, photos, files, providers, api/auth | Vercel WAF rate-limit rules (dashboard, no code); chat-send counter in code if the plan has no WAF. | Plan/Pro question
10 | 10 Medium | Security | Contact-detail blocking misses public profile text, names, service text, references and chat photos, so contact details can leak and skip the commission. | contract/my-profile.ts; providers/profile.ts; items.ts; users.ts | Call assertNoContactDetails on those fields (impressum and tax number exempt). Photos stay a known limit. | No
11 | 11 Medium | Security | A read-only Reviewer sees providers' Stripe account id, tax number, VAT id. | admin/resources.ts:73-90 | Return an explicit field list; payment/tax fields for Administrators only. | No
12 | 12 Medium | Security | Uploads are fully buffered before the size cap; a missing Content-Length is accepted. | app-request.ts:52-57; photos.ts; documents.ts | Reject uploads without Content-Length; lower the pixel cap to about 25 MP; WAF size rule. | No
13 | 13 Medium | Security | Preview builds share live storage, email and cron keys with Production. | Vercel env vars | Untick Preview on those variables; add Preview-only test values. Check the Stripe key prefix (test only on Preview). | Owner action
14 | 14 Medium | Security | Content-Security-Policy has no script-src. | next.config.ts | Trial Content-Security-Policy-Report-Only with script-src, then enforce. | No
15 | 15 Medium | Database | Row policies let either side edit more booking/request/quote columns than the domain allows (pay_by, answer_by, status). Safe today only because the code behaves. | db/src/rls.ts | Move pay_by, accepted_at, answer_by, counter_by, status to staff-only columns or add a transition trigger. | No
16 | 16 Medium | Database | translation_requests is readable by everyone and writable with any key (rate-limit poisoning). | rls.ts INSERT_ONLY_TABLES | Drop the public read policy; restrict inserts to own key or move to owner-connection writes. | No
17 | 17 Medium | Database | Money tables have thin constraints: no unique payment_ref, no range checks, free-text currency. | schema/bookings.ts, payments.ts | Add UNIQUE(payment_ref) and CHECK constraints as NOT VALID, then VALIDATE (SQL in the database audit). | No
18 | 18 Medium | Database | Migration steps are not atomic: applyRls runs about 150 statements one by one (brief permission gaps); status/kind CHECK changes lock notifications. | db/src/migrate.ts, rls.ts | Wrap applyRls in one transaction; add new checks NOT VALID then VALIDATE. | No
19 | 19 Medium | Database | Two providers publishing the same name can collide on the slug (500). | set_provider_published | Advisory lock or retry on error 23505. | No
20 | 20 Medium | Flow | Account screen hides failures: if /me fails nothing shows, and the 'Offer services' error text sits inside the loaded-only block with a generic message. Likely source of the owner's error. | account-screen.tsx:45,62-68,100,107; lib/start-offering.ts | Show retry for a failed /me; move error text outside; map error codes to specific messages. Retest with the server log. | No
21 | 21 Medium | Efficiency | No list has a limit or pagination; opening one booking/chat downloads whole lists; no read-one routes. | bookings.ts:67; requests.ts:153; threads.ts:66; booking-detail.tsx; thread.tsx | Add GET single booking and thread, return the thread id with the booking, cursor pagination. | No
22 | 22 Medium | Efficiency | Search recomputes 500 candidates per page, drops providers beyond 500, labels everyone 'new'. | search.ts:70-80,135 | Cache the offerable flag, GiST index, paginate in SQL, show the rating. | No
23 | 23 Medium | Efficiency | Public site pages are rendered per visitor (layout reads headers()). | (site)/layout.tsx:14 | Take the language from the path; cache provider pages and refresh on change. | No
24 | 24 Medium | Efficiency | Daily cron does everything in one function with one 30 s budget; a backlog can starve commission invoices; some tables are never cleaned up. | timers.ts:337-353 | Split into separate routes/budgets; partial indexes; retention clean-up. | No
25 | 25 Medium | Flow | A request cannot be withdrawn by the customer or declined by the provider; the provider cannot open a dispute from the UI (README says either side). | requests routes; disputes.ts | Decide the intended rules, add the routes and buttons. | Yes
26 | 26 Low | Flow | Invalid byte shows as a question mark in the service editor. | service-screen.tsx:160 | Replace with an ellipsis; save as UTF-8. | No
27 | 27 Low | Flow | Smaller button gaps: notify-me starts 'off'; resend code has no busy state; accept/Book taps can double-push; admin sign-in errors always German. | notify-me.tsx; verify-email-screen.tsx; request-detail.tsx:49; auth-provider.ts | Add busy/disabled states and load the saved state. | No
28 | 28 Low | Security | Origin guard passes requests with no Origin header; GET lists change state; private-link responses lack no-store; blocked-contact text stored forever; admin user id not validated; internal ids exposed. | origin.ts:7; requests.ts:153; files/[id]/route.ts; flags.ts; admin/users.ts:59 | Small fixes, listed per item in the code security audit. | No
29 | 29 Low | Security | Cron route 'suspensions' has no maxDuration; HSTS lacks includeSubDomains; .env.example misses keys. | api/cron/suspensions; next.config.ts; .env.example | One-line fixes. | No
30 | 30 Low | Duplication | Cron secret check copied twice; partyOf/sideOf and lockRow duplicated; notFound/HOUR/DAY/NO_ID redefined in 15 files; cancellation constants copied into the mobile app. | cron routes; bookings.ts/finish.ts; booking-status.ts | Keep one helper each; move the constants to @kando/contract. | No
31 | 31 Low | Efficiency | Mobile ships 311 admin/email texts it never shows; the domain barrel exports test hooks (bundle size unmeasured). | mobile i18n/index.ts; domain index.ts | Split the catalogue; separate testing entry; measure before acting. | No
32 | 32 Low | Country-ready | Quote currency EUR and search country DE are hard-coded. | requests.ts:208; search.ts:37,134,143 | Take currency/country from the provider's country (second market later). | No
33 | 33 Info | Hosting | Items only the dashboards can show: preview database branch, Stripe key prefix, bypass secret, fork-PR protection, build-log exposure, cron runs, Neon Auth cookie flags and login limits, staff second factor. | Vercel, Neon, Stripe dashboards | Owner checks them (list in the hosting and code security audits). | Owner action

## Checked and sound
What was verified and found sound
All automated tests pass (flow check: i18n 15, contract 21, domain 233, web 733, mobile 286).
Every mobile API call matches an existing route and method.
All 61 app routes use the shared guard (session, origin, size, RLS); no way found to read or change another user's data.
Admin access is re-checked on every call; staff chat access needs a recorded reason.
Stripe webhook is verified by signature, replay-safe, amounts checked.
Cron endpoints need the secret (timing-safe); live endpoint checks gave 401/403/404/400 as designed.
All policy tables have RLS; app_user has no superuser or bypass; 10 SECURITY DEFINER functions pin search_path.
No secret found in git history; security headers served; previews behind login.